## T&A
|  |  | 087/224/230 | 09T3351/09T3349 | (190/191)
Responsible | Activity | Date | Revsied T&A as per Dev.FB | Responsible | Activity | Date
ISM | AA Placement - From NY | 2021-08-17 | 09T0006/09T0007/09T3490/09TB068 | ISM | TP passing to BEL | Monday, August 30, 2021
Bulk Leader | AA Placement - SL | 2021-08-18 |  | Development | LD chart completion | Tuesday, August 31, 2021
Development | Development confirmation | 2021-08-18 |  | Development | PLM Completion with health check - Fabric & Sewing | Thursday, September 02, 2021
Planner | PCD indication | 2021-08-18 |  | Bulk | IPC Submission | 2021-09-03
Bulk Leader | PPP Meeting | 2021-08-19 |  |  | IPC LIVE | 2021-09-03
Development | PLM Completion with health check - Fabric & Sewing | 2021-08-19 | 2021-08-25 |  | YY REQ | 2021-09-03
Development | Cost Log confirmation - New format all 4 accounts | 2021-08-19 | 2021-08-25 |  | YY Confirm | 2021-09-06
Development | EPM Chart confirmation - Standardize Format | 2021-08-19 | 2021-08-25 |  | IP submission | 2021-09-07
Development | Master packing BOM confirmation - New format all 4 accounts | 2021-08-19 | 2021-08-25 |  | IP live | 2021-09-08
IE | SMV & Thread YY confirmation Standardize Format | 2021-08-19 |  |  | IP sharing with cross functional team | 2021-09-09
Sourcing | RM confirmation(before 12.00pm) | 2021-08-20 |  |  | Planning & Scheduling | 2021-09-10
Planner | Delivery Quote(before 12.00pm) | 2021-08-23 |  | Sourcing | Supplier PO | 2021-09-13
ISM | Delivery confirmation | 2021-08-27 |  | Sourcing | Possible RM I/H
Bulk Merchant | IPC creation and Submission - Except PO related items | 2021-08-23 | 2021-08-26 | Planning | Possible Delivery
Bulk Merchant | IPC creation Live | 2021-08-23 | 2021-08-27
Bulk Merchant | YY request | 2021-08-24 | 2021-08-27
Garment Tech | YY Confirmation | 2021-08-25 | 2021-08-30
Bulk Merchant | Input Submission(Samples) | 2021-08-26 | 2021-08-31
Bulk Merchant | Input Live (Samples) | 2021-08-27 | 2021-09-01
Bulk Merchant | Input Submission-Bulk | 2021-08-26 | 2021-08-31
Bulk Merchant | Input Live | 2021-08-27 | 2021-09-01
Bulk Merchant | Input Sharing with cross functional teams | 2021-08-30 | 2021-09-02
Planner | FR Planning | 2021-08-31 | 2021-09-03
Sourcing | PO release | 2021-09-01 | 2021-09-06
Formulas:
Date = [Date, row above]
Date = [Date, row above]+4

## Summary
30
Sum of Total Pcs
Model # | RMIH - SL | RMIH - IND | Req AC Date | Cfm AC Date | DEL-RM IH | DEL-REC AC | Comment2 | Total
SK0153T | 2021-12-01 | (blank) | 2022-01-03 | 2022-01-03 | 33 | 0 | (blank) | 829
SK0155T | 2021-12-01 | (blank) | 2022-01-03 | 2022-01-10 | 40 | 7 | Emb style_Delivery quote based on LT | 1105
UK0002T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 7330
UK0002T | (blank) | 2022-01-14 | 2022-01-03 | 2022-02-08 | 25 | 36 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 2182
UK0087T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 21228
UK0087T | (blank) | 2021-12-18 | 2022-01-03 | 2022-01-18 | 31 |  |  | 12864
UK0189T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 1659
UK0190T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 4704
UK0190T | (blank) | 2022-01-14 | 2022-01-03 | 2022-02-08 | 25 | 36 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 2781
UK0190T | (blank) | (blank) | 2022-01-03 | TBC | #VALUE! | #VALUE! | On hold under Development comments | 12153
UK0191T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 5460
UK0191T | (blank) | 2022-01-14 | 2022-01-03 | 2022-02-08 | 25 | 36 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 2016
UK0194T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 1292
UK0223T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 2745
UK0224T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 780
UK0230T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 462
UK0244T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 45980
UK0244T | (blank) | 2021-12-18 | 2022-01-03 | 2022-01-18 | 31 |  |  | 17680
UK0245T | (blank) | 2021-12-27 | 2022-01-03 | 2022-01-11 | 15 | 8 | Supplier confirmed based on LT. Air option advised. Requested PCD 28 days advanced from STL. | 45
UK0246T | (blank) | 2021-11-25 | 2022-01-03 | 2022-01-04 | 40 | 1 | (blank) | 11255
UW0020T | 2021-11-21 | (blank) | 2022-01-03 | 2022-01-03 | 43 | 0 | (blank) | 384
UW0020T | 2021-11-26 | (blank) | 2022-01-03 | 2022-01-03 | 38 | 0 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 14217
UW0021T | 2021-11-22 | (blank) | 2022-01-03 | 2022-01-03 | 42 | 0 | (blank) | 6509
UW0021T | 2021-11-26 | (blank) | 2022-01-03 | 2022-01-03 | 38 | 0 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 705
Grand Total | [7 empty] | 176365
6979
3.957%

## Sheet5
Program Name | Model # | Merchant | Sum of Total Pcs
ATHLETIC | UK0002T | Sheshan | 5000
Hanging Boxers | UW0021T | Thamal | 7214
Modern Essentials | SK0153T | Nilushi | 829
Modern Essentials | SK0155T | Sheshan | 1105
Modern Essentials | UK0194T | Bhagya | 1292
Thu Cotton Classics | UK0002T | Sheshan | 4512
Thu Cotton Classics | UK0087T | Sheshan | 34092
Thu Cotton Classics | UK0230T | Nilushi | 462
Thu Cotton Classics | UK0244T | Sheshan | 63660
Thu Cotton Classics | UK0245T | Thamal | 45
Thu Cotton Classics | UK0246T | Thamal | 11255
Thu Cotton Classics | UW0020T | Bhagya | 14601
Thu Cotton Stretch | UK0189T | Thamal | 1659
Thu Cotton Stretch | UK0190T | Thamal | 19638
Thu Cotton Stretch | UK0191T | Sheshan | 7476
Thu Micro | UK0223T | Bhagya | 2745
Thu Micro | UK0224T | Bhagya | 780
Grand Total |  |  | 176365

## Total Buy
[6 empty] | Edit by Brandix | [43 empty] | Bulk |  |  |  |  | Bulk | [5 empty] | planning |  | Bulk | Sourcing | [5 empty] | Bulk
CON | AA | AA-brandix ref: | Buy Plan | Vendor | Vendor Name | TP Style | Style | Program Name | Color | NRF Color | Color Name | Dimension | Size | UPC | Ship to | Office | Qty | Final Qty | Need By | In DC Date | Req Sail By | Req AC Date | Cfm Sail By | Cfm AC Date | Buy Period | Prepack Style | Prepack Color | Prepack Description | Licensee | Cost Folio Season | Comment | Process Step | PpP | Total Pcs | Plant | MCQ | Qty add | Liability value | Surcharge | RM item | Confirm Plant | Base FOB | Final FOB | Reason For Not meeting req sail by | Brandix Comment | Region comment | Brandix comments | PO # | Dev Comment | FOB con | revised Destination | FOB con | Base FOB | final FOB | Con | Model # | PPP | QTY-PCS | Merchant | Buy Name | PSD | comments for RM date | SPO | RMIH - SL | RMIH - IND | RMIH AIR | Actual RM LT | Standered RM LT | Act LT Vs STD LT | T&A Deliver | req: del to actual del | T&A del vs actual (weeks) | Req:del | act: Del | Style::NRF | Comment | DEL-RM IH | DEL-REC AC
26819609T4159001001 | 268196 | 268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | MD | 194999093362 | 46 | JAP | 5 | 5 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 15 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | LP00023295 | #N/A | 09T4159001 | JAP |  | 6.91 | quoted price need to be correct.need to write separately | 09T4159001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::001 |  | 40 | 1
26819609T4159001001 | 268196 | 268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 194999093379 | 46 | JAP | 5 | 5 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 15 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | LP00023295 | #N/A | 09T4159001 | JAP |  | 6.91 |  | 09T4159001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::001 |  | 40 | 1
26819609T4159001001 | 268196 | 268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 194999093386 | 46 | JAP | 5 | 5 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 15 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | LP00023295 | #N/A | 09T4159001 | JAP |  | 6.91 |  | 09T4159001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::001 |  | 40 | 1
26819609T4159608608 | 268196 | 268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | MD | 194999093614 | 46 | JAP | 5 | 5 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 15 | BEL | Yes | 2144.9351 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | LP00023297 | #N/A | 09T4159608 | JAP |  | 6.91 |  | 09T4159608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4159::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26819609T4159608608 | 268196 | 268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | LG | 194999093621 | 46 | JAP | 5 | 5 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 15 | BEL | Yes | 2144.9351 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | LP00023297 | #N/A | 09T4159608 | JAP |  | 6.91 |  | 09T4159608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4159::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26819609T4159608608 | 268196 | 268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XL | 194999093638 | 46 | JAP | 5 | 5 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 15 | BEL | Yes | 2144.9351 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | LP00023297 | #N/A | 09T4159608 | JAP |  | 6.91 |  | 09T4159608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4159::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26819609TQ004U76462 | 268196 | 268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TQ004 | 09TQ004 | Thu Cotton Classics | U76 | 462 | INK BLUE | * | MD | 088541601627 | 46 | JAP | 5 | 5 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-18 | 2022-01-11 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 15 | BEL | Yes | 6604.1483 | 15443.0583 | 1029.5372 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  | 8/25 Customer confirmed to drop the style. | Qty Dropped | #N/A | 09TQ004462 | JAP |  | 8.18 |  | 09TQ004462 | UK0245T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-27 | 2021-12-09 | 116 | 116 | 0 | 2022-01-30 | -1.1429 | 19 | 2022-01-03 | 2022-01-11 | 09TQ004::462 | Supplier confirmed based on LT. Air option advised. Requested PCD 28 days advanced from STL. | 15 | 8
26819609TQ004U76462 | 268196 | 268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TQ004 | 09TQ004 | Thu Cotton Classics | U76 | 462 | INK BLUE | * | LG | 088541601634 | 46 | JAP | 5 | 5 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-18 | 2022-01-11 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 15 | BEL | Yes | 6604.1483 | 15443.0583 | 1029.5372 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  | 8/25 Customer confirmed to drop the style. | Qty Dropped | #N/A | 09TQ004462 | JAP |  | 8.18 |  | 09TQ004462 | UK0245T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-27 | 2021-12-09 | 116 | 116 | 0 | 2022-01-30 | -1.1429 | 19 | 2022-01-03 | 2022-01-11 | 09TQ004::462 | Supplier confirmed based on LT. Air option advised. Requested PCD 28 days advanced from STL. | 15 | 8
26819609TQ004U76462 | 268196 | 268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TQ004 | 09TQ004 | Thu Cotton Classics | U76 | 462 | INK BLUE | * | XL | 088541601641 | 46 | JAP | 5 | 5 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-18 | 2022-01-11 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 15 | BEL | Yes | 6604.1483 | 15443.0583 | 1029.5372 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  | 8/25 Customer confirmed to drop the style. | Qty Dropped | #N/A | 09TQ004462 | JAP |  | 8.18 |  | 09TQ004462 | UK0245T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-27 | 2021-12-09 | 116 | 116 | 0 | 2022-01-30 | -1.1429 | 19 | 2022-01-03 | 2022-01-11 | 09TQ004::462 | Supplier confirmed based on LT. Air option advised. Requested PCD 28 days advanced from STL. | 15 | 8
268197-269604 09TF001A99099 | 268197-269604 | 268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | Thu Cotton Classics | A99 | 099 | MULTI | * | SM | 088541316606 | MEXICO | DRESS | 800 | 800 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW | 4 | 3200 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | LP00023299 | #N/A | 09TF001099 | MEX |  | 8.04 |  | 09TF001099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09TF001::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
268197-269604 09TF001A99099 | 268197-269604 | 268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | Thu Cotton Classics | A99 | 099 | MULTI | * | MD | 088541316613 | MEXICO | DRESS | 890 | 890 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW | 4 | 3560 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | LP00023299 | #N/A | 09TF001099 | MEX |  | 8.04 |  | 09TF001099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09TF001::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
268197-269604 09TF001A99099 | 268197-269604 | 268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | Thu Cotton Classics | A99 | 099 | MULTI | * | LG | 088541316620 | MEXICO | DRESS | 1140 | 1140 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW | 4 | 4560 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | LP00023299 | #N/A | 09TF001099 | MEX |  | 8.04 |  | 09TF001099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09TF001::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
268197-269604 09TF001A99099 | 268197-269604 | 268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | Thu Cotton Classics | A99 | 099 | MULTI | * | XL | 088541316637 | MEXICO | DRESS | 590 | 590 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW | 4 | 2360 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | LP00023299 | #N/A | 09TF001099 | MEX |  | 8.04 |  | 09TF001099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09TF001::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
268197-269604 09TF001100100 | 268197-269604 | 268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | Thu Cotton Classics | 100 | 100 | WHITE | * | SM | 088541316651 | MEXICO | DRESS | 400 | 400 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW | 4 | 1600 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | LP00023298 | #N/A | 09TF001100 | MEX |  | 7.72 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
268197-269604 09TF001100100 | 268197-269604 | 268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | Thu Cotton Classics | 100 | 100 | WHITE | * | MD | 088541316668 | MEXICO | DRESS | 420 | 420 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW | 4 | 1680 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | LP00023298 | #N/A | 09TF001100 | MEX |  | 7.72 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
268197-269604 09TF001100100 | 268197-269604 | 268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | Thu Cotton Classics | 100 | 100 | WHITE | * | LG | 088541316675 | MEXICO | DRESS | 470 | 470 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW | 4 | 1880 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | LP00023298 | #N/A | 09TF001100 | MEX |  | 7.72 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
268197-269604 09TF001100100 | 268197-269604 | 268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | Thu Cotton Classics | 100 | 100 | WHITE | * | XL | 088541316682 | MEXICO | DRESS | 120 | 120 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW | 4 | 480 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | LP00023298 | #N/A | 09TF001100 | MEX |  | 7.72 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
26820109T0006099099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | S | 088541003544 | 46 | DRESS | 312 | 312 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 1248 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | 154054 | #N/A | 09T0006099 | US WHOLESALE |  | 8.9 |  | 09T0006099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09T0006::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
26820109T0006099099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | M | 088541003551 | 46 | DRESS | 1210 | 1210 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 4840 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | 154054 | #N/A | 09T0006099 | US WHOLESALE |  | 8.9 |  | 09T0006099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09T0006::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
26820109T0006099099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | L | 088541003568 | 46 | DRESS | 969 | 969 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 3876 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | 154054 | #N/A | 09T0006099 | US WHOLESALE |  | 8.9 |  | 09T0006099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09T0006::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
26820109T0006099099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | XL | 088541003575 | 46 | DRESS | 593 | 593 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 2372 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | 154054 | #N/A | 09T0006099 | US WHOLESALE |  | 8.9 |  | 09T0006099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09T0006::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
26820109T0006099099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | 2XL | 088541003582 | 46 | DRESS | 132 | 132 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 528 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | 154054 | #N/A | 09T0006099 | US WHOLESALE |  | 8.9 |  | 09T0006099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09T0006::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
26820109T0007099099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | S | 088541003599 | 46 | DRESS | 586 | 586 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 2344 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154055 | #N/A | 09T0007099 | US WHOLESALE |  | 7.8 |  | 09T0007099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09T0007::099 |  | 40 | 1
26820109T0007099099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | M | 088541003605 | 46 | DRESS | 2035 | 2035 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 8140 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154055 | #N/A | 09T0007099 | US WHOLESALE |  | 7.8 |  | 09T0007099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09T0007::099 |  | 40 | 1
26820109T0007099099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | L | 088541003612 | 46 | DRESS | 1265 | 1265 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 5060 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154055 | #N/A | 09T0007099 | US WHOLESALE |  | 7.8 |  | 09T0007099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09T0007::099 |  | 40 | 1
26820109T0007099099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | XL | 088541003629 | 46 | DRESS | 850 | 850 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 3400 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154055 | #N/A | 09T0007099 | US WHOLESALE |  | 7.8 |  | 09T0007099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09T0007::099 |  | 40 | 1
30 | PSR Plugin | Method Name:PopulateRibbonDropDownItem.Request Status:Failed because of- Cannot implicitly convert type 'System.DateTime' to 'string' | Exception Stack-Trace: at CallSite.Target(Closure , CallSite , Object ) at System.Dynamic.UpdateDelegates.UpdateAndExecute1[T0,TRet](CallSite site, T0 arg0) at CallSite.Target(Closure , CallSite , Object ) at NGC.OfflineDataPlugin.PluginMethods.GetColumnForSorting() at NGC.OfflineDataPlugin.PluginButtons.PopulateRibbonDropDownItem() at NGC.OfflineDataPlugin.PluginButtons.RibbonDropDownItem() | 2021-08-30 13:25 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | 2XL | 088541003636 | 46 | DRESS | 571 | 571 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 2284 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154055 | #N/A | 09T0007099 | US WHOLESALE |  | 7.8 |  | 09T0007099 | UK0087T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09T0007::099 |  | 40 | 1
26820109T3108CHS410 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | CHS | 410 | DARK NAVY | * | SM | 088541378727 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 60 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108410 | US WHOLESALE |  | 3.26 |  | 09T3108410 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::410 |  | 40 | 1
26820109T3108CHS410 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | CHS | 410 | DARK NAVY | * | MD | 088541378734 | 46 | DRESS | 231 | 231 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 231 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108410 | US WHOLESALE |  | 3.26 |  | 09T3108410 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::410 |  | 40 | 1
26820109T3108CHS410 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | CHS | 410 | DARK NAVY | * | LG | 088541378741 | 46 | DRESS | 539 | 539 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 539 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108410 | US WHOLESALE |  | 3.26 |  | 09T3108410 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::410 |  | 40 | 1
26820109T3108CHS410 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | CHS | 410 | DARK NAVY | * | XL | 088541378758 | 46 | DRESS | 683 | 683 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 683 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108410 | US WHOLESALE |  | 3.26 |  | 09T3108410 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::410 |  | 40 | 1
26820109T3108CIX432 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | CIX | 432 | French Blue | * | SM | 088541378772 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 60 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108432 | US WHOLESALE |  | 3.26 |  | 09T3108432 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::432 |  | 40 | 1
26820109T3108CIX432 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | CIX | 432 | French Blue | * | MD | 088541378789 | 46 | DRESS | 362 | 362 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 362 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108432 | US WHOLESALE |  | 3.26 |  | 09T3108432 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::432 |  | 40 | 1
26820109T3108CIX432 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | CIX | 432 | French Blue | * | LG | 088541378796 | 46 | DRESS | 395 | 395 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 395 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108432 | US WHOLESALE |  | 3.26 |  | 09T3108432 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::432 |  | 40 | 1
26820109T3108CIX432 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | CIX | 432 | French Blue | * | XL | 088541378802 | 46 | DRESS | 329 | 329 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 329 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108432 | US WHOLESALE |  | 3.26 |  | 09T3108432 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::432 |  | 40 | 1
26820109T3108P7A004 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | P7A | 004 | Grey Heather | * | MD | 088541378680 | 46 | DRESS | 417 | 417 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 417 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154052 | #N/A | 09T3108004 | US WHOLESALE |  | 3.28 |  | 09T3108004 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 119 | -15 | 2022-02-02 | -5.1429 | -6 | 2022-01-03 | 2022-02-08 | 09T3108::004 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T3108P7A004 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | P7A | 004 | Grey Heather | * | LG | 088541378697 | 46 | DRESS | 660 | 660 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 660 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154052 | #N/A | 09T3108004 | US WHOLESALE |  | 3.28 |  | 09T3108004 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 119 | -15 | 2022-02-02 | -5.1429 | -6 | 2022-01-03 | 2022-02-08 | 09T3108::004 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T3108P7A004 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | P7A | 004 | Grey Heather | * | XL | 088541378703 | 46 | DRESS | 105 | 105 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 105 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154052 | #N/A | 09T3108004 | US WHOLESALE |  | 3.28 |  | 09T3108004 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 119 | -15 | 2022-02-02 | -5.1429 | -6 | 2022-01-03 | 2022-02-08 | 09T3108::004 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T3108XCN608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | XCN | 608 | Mahogany | * | MD | 088541378833 | 46 | DRESS | 221 | 221 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 221 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108608 | US WHOLESALE |  | 3.26 |  | 09T3108608 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::608 |  | 40 | 1
26820109T3108XCN608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | XCN | 608 | Mahogany | * | LG | 088541378840 | 46 | DRESS | 109 | 109 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 109 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108608 | US WHOLESALE |  | 3.26 |  | 09T3108608 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::608 |  | 40 | 1
26820109T3108XCN608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09T3108 | Thu Cotton Classics | XCN | 608 | Mahogany | * | XL | 088541378857 | 46 | DRESS | 341 | 341 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 341 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154053 | #N/A | 09T3108608 | US WHOLESALE |  | 3.26 |  | 09T3108608 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::608 |  | 40 | 1
26820109T3255469469 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09T3255 | Hanging Boxers | 469 | 469 | ICE | * | XXL | 088541450966 | 46 | DRESS | 261 | 261 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 261 | BEL | Yes | 5263.4545 | 7834.5467 | 3.4651 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154047 | #N/A | 09T3255469 | US WHOLESALE |  | 3.46 |  | 09T3255469 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::469 |  | 42 | 0
26820109T3255608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09T3255 | Hanging Boxers | 608 | 608 | MAHOGANY | * | MD | 088541451031 | 46 | DRESS | 227 | 227 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 227 | BEL | Yes | 7013.4545 | 10439.3867 | 20.4293 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154047 | #N/A | 09T3255608 | US WHOLESALE |  | 3.46 |  | 09T3255608 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::608 |  | 42 | 0
26820109T3255608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09T3255 | Hanging Boxers | 608 | 608 | MAHOGANY | * | LG | 088541451048 | 46 | DRESS | 224 | 224 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 224 | BEL | Yes | 7013.4545 | 10439.3867 | 20.4293 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154047 | #N/A | 09T3255608 | US WHOLESALE |  | 3.46 |  | 09T3255608 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::608 |  | 42 | 0
26820109T3255608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09T3255 | Hanging Boxers | 608 | 608 | MAHOGANY | * | XXL | 088541451062 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 60 | BEL | Yes | 7013.4545 | 10439.3867 | 20.4293 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154047 | #N/A | 09T3255608 | US WHOLESALE |  | 3.46 |  | 09T3255608 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::608 |  | 42 | 0
26820109T3255410587 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09T3255 | Hanging Boxers | 410 | 587 | SAILOR NAVY | * | MD | 088541450980 | 46 | DRESS | 312 | 312 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 312 | BEL | Yes | 3787.4545 | 5637.5502 | 1.5086 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154047 | #N/A | 09T3255587 | US WHOLESALE |  | 3.46 |  | 09T3255587 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::587 |  | 42 | 0
26820109T3255410587 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09T3255 | Hanging Boxers | 410 | 587 | SAILOR NAVY | * | LG | 088541450997 | 46 | DRESS | 308 | 308 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 308 | BEL | Yes | 3787.4545 | 5637.5502 | 1.5086 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154047 | #N/A | 09T3255587 | US WHOLESALE |  | 3.46 |  | 09T3255587 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::587 |  | 42 | 0
26820109T3255410587 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09T3255 | Hanging Boxers | 410 | 587 | SAILOR NAVY | * | XL | 088541451000 | 46 | DRESS | 117 | 117 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 117 | BEL | Yes | 3787.4545 | 5637.5502 | 1.5086 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154047 | #N/A | 09T3255587 | US WHOLESALE |  | 3.46 |  | 09T3255587 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::587 |  | 42 | 0
26820109T3257F1S435 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3257 | 09T3257 | Hanging Boxers | F1S | 435 | INDIGO | * | SM | 088541451079 | 46 | DRESS | 84 | 84 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 84 | BEL | Yes | 2304.7818 | 3216.2078 | 4.562 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154048 | #N/A | 09T3257435 | US WHOLESALE |  | 3.31 |  | 09T3257435 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09T3257::435 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109T3257F1S435 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3257 | 09T3257 | Hanging Boxers | F1S | 435 | INDIGO | * | MD | 088541451086 | 46 | DRESS | 136 | 136 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 136 | BEL | Yes | 2304.7818 | 3216.2078 | 4.562 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154048 | #N/A | 09T3257435 | US WHOLESALE |  | 3.31 |  | 09T3257435 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09T3257::435 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109T3257F1S435 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3257 | 09T3257 | Hanging Boxers | F1S | 435 | INDIGO | * | LG | 088541451093 | 46 | DRESS | 150 | 150 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 150 | BEL | Yes | 2304.7818 | 3216.2078 | 4.562 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154048 | #N/A | 09T3257435 | US WHOLESALE |  | 3.31 |  | 09T3257435 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09T3257::435 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109T3257F1S435 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3257 | 09T3257 | Hanging Boxers | F1S | 435 | INDIGO | * | XL | 088541451109 | 46 | DRESS | 335 | 335 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 335 | BEL | Yes | 2304.7818 | 3216.2078 | 4.562 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154048 | #N/A | 09T3257435 | US WHOLESALE |  | 3.31 |  | 09T3257435 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09T3257::435 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109T3281YC7100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | 09T3281 | Modern Essentials | YC7 | 100 | White | * | SM | 088541492652 | 46 | DRESS | 116 | 116 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-17 | 2022-01-10 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 116 | BEL | [5 empty] | 10703 - Brandix Apparel Solutions Limited - Essentials, Nivithigala |  |  |  | Meeting the T&A delivery |  |  | 154049 | #N/A | 09T3281100 | US WHOLESALE |  | 7.21 |  | 09T3281100 | SK0155T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 | 2021-12-01 |  |  | 94 | 94 | 0 | 2022-01-08 | -1 | -2 | 2022-01-03 | 2022-01-10 | 09T3281::100 | Emb style_Delivery quote based on LT | 40 | 7
26820109T3281YC7100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | 09T3281 | Modern Essentials | YC7 | 100 | White | * | MD | 088541492669 | 46 | DRESS | 328 | 328 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-17 | 2022-01-10 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 328 | BEL | [5 empty] | 10703 - Brandix Apparel Solutions Limited - Essentials, Nivithigala |  |  |  | Meeting the T&A delivery |  |  | 154049 | #N/A | 09T3281100 | US WHOLESALE |  | 7.21 |  | 09T3281100 | SK0155T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 | 2021-12-01 |  |  | 94 | 94 | 0 | 2022-01-08 | -1 | -2 | 2022-01-03 | 2022-01-10 | 09T3281::100 | Emb style_Delivery quote based on LT | 40 | 7
26820109T3281YC7100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | 09T3281 | Modern Essentials | YC7 | 100 | White | * | LG | 088541492676 | 46 | DRESS | 439 | 439 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-17 | 2022-01-10 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 439 | BEL | [5 empty] | 10703 - Brandix Apparel Solutions Limited - Essentials, Nivithigala |  |  |  | Meeting the T&A delivery |  |  | 154049 | #N/A | 09T3281100 | US WHOLESALE |  | 7.21 |  | 09T3281100 | SK0155T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 | 2021-12-01 |  |  | 94 | 94 | 0 | 2022-01-08 | -1 | -2 | 2022-01-03 | 2022-01-10 | 09T3281::100 | Emb style_Delivery quote based on LT | 40 | 7
26820109T3281YC7100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | 09T3281 | Modern Essentials | YC7 | 100 | White | * | XL | 088541492683 | 46 | DRESS | 115 | 115 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-17 | 2022-01-10 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 115 | BEL | [5 empty] | 10703 - Brandix Apparel Solutions Limited - Essentials, Nivithigala |  |  |  | Meeting the T&A delivery |  |  | 154049 | #N/A | 09T3281100 | US WHOLESALE |  | 7.21 |  | 09T3281100 | SK0155T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 | 2021-12-01 |  |  | 94 | 94 | 0 | 2022-01-08 | -1 | -2 | 2022-01-03 | 2022-01-10 | 09T3281::100 | Emb style_Delivery quote based on LT | 40 | 7
26820109T3281YC7100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | 09T3281 | Modern Essentials | YC7 | 100 | White | * | XXL | 088541492690 | 46 | DRESS | 107 | 107 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-17 | 2022-01-10 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 107 | BEL | [5 empty] | 10703 - Brandix Apparel Solutions Limited - Essentials, Nivithigala |  |  |  | Meeting the T&A delivery |  |  | 154049 | #N/A | 09T3281100 | US WHOLESALE |  | 7.21 |  | 09T3281100 | SK0155T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 | 2021-12-01 |  |  | 94 | 94 | 0 | 2022-01-08 | -1 | -2 | 2022-01-03 | 2022-01-10 | 09T3281::100 | Emb style_Delivery quote based on LT | 40 | 7
26820109T3283CHS410 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3283 | 09T3283 | Modern Essentials | CHS | 410 | DARK NAVY | * | SM | 088541492751 | 46 | DRESS | 221 | 221 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 221 | BEL | Yes | 4503.7418 | 944.0834 | 1.1388 | Fabric | 10703 - Brandix Apparel Solutions Limited - Essentials, Nivithigala |  |  |  | On time |  |  | 154050 | #N/A | 09T3283410 | US WHOLESALE |  | 5.39 |  | 09T3283410 | SK0153T |  |  | Nilushi | Aug-Basic |  |  | 2021-09-01 | 2021-12-01 |  |  | 94 | 94 | 0 | 2022-01-08 | 0 | 5 | 2022-01-03 | 2022-01-03 | 09T3283::410 |  | 33 | 0
26820109T3283CHS410 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3283 | 09T3283 | Modern Essentials | CHS | 410 | DARK NAVY | * | MD | 088541492768 | 46 | DRESS | 212 | 212 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 212 | BEL | Yes | 4503.7418 | 944.0834 | 1.1388 | Fabric | 10703 - Brandix Apparel Solutions Limited - Essentials, Nivithigala |  |  |  | On time |  |  | 154050 | #N/A | 09T3283410 | US WHOLESALE |  | 5.39 |  | 09T3283410 | SK0153T |  |  | Nilushi | Aug-Basic |  |  | 2021-09-01 | 2021-12-01 |  |  | 94 | 94 | 0 | 2022-01-08 | 0 | 5 | 2022-01-03 | 2022-01-03 | 09T3283::410 |  | 33 | 0
26820109T3283CHS410 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3283 | 09T3283 | Modern Essentials | CHS | 410 | DARK NAVY | * | LG | 088541492775 | 46 | DRESS | 301 | 301 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 301 | BEL | Yes | 4503.7418 | 944.0834 | 1.1388 | Fabric | 10703 - Brandix Apparel Solutions Limited - Essentials, Nivithigala |  |  |  | On time |  |  | 154050 | #N/A | 09T3283410 | US WHOLESALE |  | 5.39 |  | 09T3283410 | SK0153T |  |  | Nilushi | Aug-Basic |  |  | 2021-09-01 | 2021-12-01 |  |  | 94 | 94 | 0 | 2022-01-08 | 0 | 5 | 2022-01-03 | 2022-01-03 | 09T3283::410 |  | 33 | 0
26820109T3283CHS410 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3283 | 09T3283 | Modern Essentials | CHS | 410 | DARK NAVY | * | XXL | 088541492799 | 46 | DRESS | 95 | 95 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 1 | 95 | BEL | Yes | 4503.7418 | 944.0834 | 1.1388 | Fabric | 10703 - Brandix Apparel Solutions Limited - Essentials, Nivithigala |  |  |  | On time |  |  | 154050 | #N/A | 09T3283410 | US WHOLESALE |  | 5.39 |  | 09T3283410 | SK0153T |  |  | Nilushi | Aug-Basic |  |  | 2021-09-01 | 2021-12-01 |  |  | 94 | 94 | 0 | 2022-01-08 | 0 | 5 | 2022-01-03 | 2022-01-03 | 09T3283::410 |  | 33 | 0
26820109T3349UB1001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3349 | 09T3349 | Thu Cotton Stretch | UB1 | 001 | Black | * | XL | 088541539296 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | Yes | 1277.6764 | 1111.5185 | 18.5253 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154061 | #N/A | 09T3349001 | US WHOLESALE |  | 6.84 |  | 09T3349001 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3349::001 |  | 40 | 1
26820109T3351001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | 09T3351 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 088541539739 | 46 | DRESS | 676 | 676 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2021-01-11 | 2021-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 2028 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd | 6.42 | 6.42 |  |  |  |  | 154243 | #N/A | 09T3351001 | US WHOLESALE |  | 6.42 |  | 09T3351001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  |  |  | #N/A | #N/A | #N/A | #N/A | 52 | #N/A | 2022-01-03 | 2021-01-04 | 09T3351::001 | On hold under Development comments | 44200 | -364
26820109T3351001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | 09T3351 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 088541539746 | 46 | DRESS | 747 | 747 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2021-01-11 | 2021-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 2241 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd | 6.42 | 6.42 |  |  |  |  | 154243 | #N/A | 09T3351001 | US WHOLESALE |  | 6.42 |  | 09T3351001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  |  |  | #N/A | #N/A | #N/A | #N/A | 52 | #N/A | 2022-01-03 | 2021-01-04 | 09T3351::001 | On hold under Development comments | 44200 | -364
26820109T3351001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | 09T3351 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XXL | 088541539753 | 46 | DRESS | 95 | 95 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2021-01-11 | 2021-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 285 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd | 6.42 | 6.42 |  |  |  |  | 154243 | #N/A | 09T3351001 | US WHOLESALE |  | 6.42 |  | 09T3351001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  |  |  | #N/A | #N/A | #N/A | #N/A | 52 | #N/A | 2022-01-03 | 2021-01-04 | 09T3351::001 | On hold under Development comments | 44200 | -364
26820109T3351608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | 09T3351 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | LG | 088541539487 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2021-01-11 | 2021-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | Yes | 4579.6187 | 4155.8125 | 3.2852 |  | 10914 - Brandix Apparel India Pvt Ltd | 6.58 | 9.8652 |  |  |  |  | 154243 | #N/A | 09T3351608 | US WHOLESALE |  | 6.58 |  | 09T3351608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  |  |  | #N/A | #N/A | #N/A | #N/A | 52 | #N/A | 2022-01-03 | 2021-01-04 | 09T3351::608 | On hold under Development comments | 44200 | -364
26820109T3351608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | 09T3351 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XL | 088541539494 | 46 | DRESS | 1133 | 1133 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2021-01-11 | 2021-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 3399 | BEL | Yes | 4579.6187 | 4155.8125 | 3.2852 |  | 10914 - Brandix Apparel India Pvt Ltd | 6.58 | 9.8652 |  |  |  |  | 154243 | #N/A | 09T3351608 | US WHOLESALE |  | 6.58 |  | 09T3351608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  |  |  | #N/A | #N/A | #N/A | #N/A | 52 | #N/A | 2022-01-03 | 2021-01-04 | 09T3351::608 | On hold under Development comments | 44200 | -364
26820109T3351608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | 09T3351 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XXL | 088541539500 | 46 | DRESS | 72 | 72 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2021-01-11 | 2021-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 216 | BEL | Yes | 4579.6187 | 4155.8125 | 3.2852 |  | 10914 - Brandix Apparel India Pvt Ltd | 6.58 | 9.8652 |  |  |  |  | 154243 | #N/A | 09T3351608 | US WHOLESALE |  | 6.58 |  | 09T3351608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  |  |  | #N/A | #N/A | #N/A | #N/A | 52 | #N/A | 2022-01-03 | 2021-01-04 | 09T3351::608 | On hold under Development comments | 44200 | -364
26820109T3351464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | 09T3351 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | SM | 088541542739 | 46 | DRESS | 218 | 218 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2021-01-11 | 2021-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 654 | BEL | Yes | 873.8389 | 1034.7406 | 0.81604 |  | 10914 - Brandix Apparel India Pvt Ltd | 6.42 | 7.236 |  |  |  |  | 154243 | #N/A | 09T3351464 | US WHOLESALE |  | 6.42 |  | 09T3351464 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  |  |  | #N/A | #N/A | #N/A | #N/A | 52 | #N/A | 2022-01-03 | 2021-01-04 | 09T3351::464 | On hold under Development comments | 44200 | -364
26820109T3351464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | 09T3351 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | LG | 088541542753 | 46 | DRESS | 461 | 461 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2021-01-11 | 2021-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 1383 | BEL | Yes | 873.8389 | 1034.7406 | 0.81604 |  | 10914 - Brandix Apparel India Pvt Ltd | 6.42 | 7.236 |  |  |  |  | 154243 | #N/A | 09T3351464 | US WHOLESALE |  | 6.42 |  | 09T3351464 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  |  |  | #N/A | #N/A | #N/A | #N/A | 52 | #N/A | 2022-01-03 | 2021-01-04 | 09T3351::464 | On hold under Development comments | 44200 | -364
26820109T3351464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | 09T3351 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XL | 088541542760 | 46 | DRESS | 589 | 589 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2021-01-11 | 2021-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 1767 | BEL | Yes | 873.8389 | 1034.7406 | 0.81604 |  | 10914 - Brandix Apparel India Pvt Ltd | 6.42 | 7.236 |  |  |  |  | 154243 | #N/A | 09T3351464 | US WHOLESALE |  | 6.42 |  | 09T3351464 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  |  |  | #N/A | #N/A | #N/A | #N/A | 52 | #N/A | 2022-01-03 | 2021-01-04 | 09T3351::464 | On hold under Development comments | 44200 | -364
26820109T3490001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3490 | 09T3490 | Thu Micro | 001 | 001 | BLACK | * | XXL | 088541654623 | 46 | DRESS | 73 | 73 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 219 | BEL | Yes | 153.6952 | 140.4472 | 0.1717 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154066 | #N/A | 09T3490001 | US WHOLESALE |  | 8.34 |  | 09T3490001 | UK0224T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3490::001 |  | 40 | 1
26820109T3490499499 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3490 | 09T3490 | Thu Micro | 499 | 499 | BLUE MULTI | * | LG | 088541654753 | 46 | DRESS | 67 | 67 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 201 | BEL | Yes | 1892.5302 | 5186.5002 | 21.884 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154066 | #N/A | 09T3490499 | US WHOLESALE |  | 8.34 |  | 09T3490499 | UK0224T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3490::499 |  | 40 | 1
26820109T3490100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3490 | 09T3490 | Thu Micro | 100 | 100 | WHITE | * | MD | 088541654647 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | Yes | 1730.1656 | 1581.0308 | 13.1753 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154066 | #N/A | 09T3490100 | US WHOLESALE |  | 8.34 |  | 09T3490100 | UK0224T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3490::100 |  | 40 | 1
26820109T3490100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3490 | 09T3490 | Thu Micro | 100 | 100 | WHITE | * | XL | 088541654661 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | Yes | 1730.1656 | 1581.0308 | 13.1753 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154066 | #N/A | 09T3490100 | US WHOLESALE |  | 8.34 |  | 09T3490100 | UK0224T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3490::100 |  | 40 | 1
26820109T3492001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | 09T3492 | Thu Micro | 001 | 001 | BLACK | * | MD | 088541654890 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | Yes | 200.0086 | 140.4472 | 0.1717 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154066 | #N/A | 09T3492001 | US WHOLESALE |  | 8.52 |  | 09T3492001 | UK0223T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3492::001 |  | 40 | 1
26820109T3492001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | 09T3492 | Thu Micro | 001 | 001 | BLACK | * | LG | 088541654906 | 46 | DRESS | 125 | 125 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 375 | BEL | Yes | 200.0086 | 140.4472 | 0.1717 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154066 | #N/A | 09T3492001 | US WHOLESALE |  | 8.52 |  | 09T3492001 | UK0223T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3492::001 |  | 40 | 1
26820109T3492001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | 09T3492 | Thu Micro | 001 | 001 | BLACK | * | XXL | 088541654920 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | Yes | 200.0086 | 140.4472 | 0.1717 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154066 | #N/A | 09T3492001 | US WHOLESALE |  | 8.52 |  | 09T3492001 | UK0223T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3492::001 |  | 40 | 1
26820109T3492499499 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | 09T3492 | Thu Micro | 499 | 499 | BLUE MULTI | * | MD | 088541654999 | 46 | DRESS | 93 | 93 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 279 | BEL | Yes | 2462.8112 | 5186.5002 | 21.884 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154066 | #N/A | 09T3492499 | US WHOLESALE |  | 8.52 |  | 09T3492499 | UK0223T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3492::499 |  | 40 | 1
26820109T3492499499 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | 09T3492 | Thu Micro | 499 | 499 | BLUE MULTI | * | LG | 088541655002 | 46 | DRESS | 77 | 77 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 231 | BEL | Yes | 2462.8112 | 5186.5002 | 21.884 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154066 | #N/A | 09T3492499 | US WHOLESALE |  | 8.52 |  | 09T3492499 | UK0223T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3492::499 |  | 40 | 1
26820109T3741608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3741 | 09T3741 | Modern Essentials | 608 | 608 | MAHOGANY | * | MD | 088541946582 | 46 | DRESS | 239 | 239 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 956 | BEL | Yes | 1167.0164 | 2179.84 | 6.7487 | Fabric/Elastic | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154051 | #N/A | 09T3741608 | US WHOLESALE |  | 8.56 |  | 09T3741608 | UK0194T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3741::608 |  | 40 | 1
26820109T3741608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3741 | 09T3741 | Modern Essentials | 608 | 608 | MAHOGANY | * | LG | 088541946599 | 46 | DRESS | 84 | 84 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 336 | BEL | Yes | 1167.0164 | 2179.84 | 6.7487 | Fabric/Elastic | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154051 | #N/A | 09T3741608 | US WHOLESALE |  | 8.56 |  | 09T3741608 | UK0194T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3741::608 |  | 40 | 1
26820109T4144001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | SM | 194999091955 | 46 | DRESS | 70 | 70 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 210 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144001 | US WHOLESALE |  | 6.84 |  | 09T4144001 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::001 |  | 40 | 1
26820109T4144001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | MD | 194999091962 | 46 | DRESS | 255 | 255 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 765 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144001 | US WHOLESALE |  | 6.84 |  | 09T4144001 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::001 |  | 40 | 1
26820109T4144001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 194999091979 | 46 | DRESS | 187 | 187 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 561 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144001 | US WHOLESALE |  | 6.84 |  | 09T4144001 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::001 |  | 40 | 1
26820109T4144001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 194999091986 | 46 | DRESS | 62 | 62 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 186 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144001 | US WHOLESALE |  | 6.84 |  | 09T4144001 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::001 |  | 40 | 1
26820109T4144001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XXL | 194999091993 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144001 | US WHOLESALE |  | 6.84 |  | 09T4144001 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::001 |  | 40 | 1
26820109T4144608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | SM | 194999092259 | 46 | DRESS | 70 | 70 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 210 | BEL | Yes | 1501.7869 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4144608 | US WHOLESALE |  | 7.08 |  | 09T4144608 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4144::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4144608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | MD | 194999092266 | 46 | DRESS | 255 | 255 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 765 | BEL | Yes | 1501.7869 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4144608 | US WHOLESALE |  | 7.08 |  | 09T4144608 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4144::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4144608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | LG | 194999092273 | 46 | DRESS | 207 | 207 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 621 | BEL | Yes | 1501.7869 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4144608 | US WHOLESALE |  | 7.08 |  | 09T4144608 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4144::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4144608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XL | 194999092280 | 46 | DRESS | 80 | 80 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 240 | BEL | Yes | 1501.7869 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4144608 | US WHOLESALE |  | 7.08 |  | 09T4144608 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4144::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4144608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XXL | 194999092297 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | Yes | 1501.7869 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4144608 | US WHOLESALE |  | 7.08 |  | 09T4144608 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4144::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4144464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | SM | 194999092204 | 46 | DRESS | 70 | 70 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 210 | BEL | Yes | 242.7686 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144464 | US WHOLESALE |  | 6.84 |  | 09T4144464 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::464 |  | 40 | 1
26820109T4144464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | MD | 194999092211 | 46 | DRESS | 255 | 255 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 765 | BEL | Yes | 242.7686 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144464 | US WHOLESALE |  | 6.84 |  | 09T4144464 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::464 |  | 40 | 1
26820109T4144464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | LG | 194999092228 | 46 | DRESS | 207 | 207 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 621 | BEL | Yes | 242.7686 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144464 | US WHOLESALE |  | 6.84 |  | 09T4144464 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::464 |  | 40 | 1
26820109T4144464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XL | 194999092235 | 46 | DRESS | 80 | 80 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 240 | BEL | Yes | 242.7686 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144464 | US WHOLESALE |  | 6.84 |  | 09T4144464 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::464 |  | 40 | 1
26820109T4144464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XXL | 194999092242 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | Yes | 242.7686 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144464 | US WHOLESALE |  | 6.84 |  | 09T4144464 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::464 |  | 40 | 1
26820109T4144100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | SM | 194999092006 | 46 | DRESS | 62 | 62 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 186 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144100 | US WHOLESALE |  | 6.84 |  | 09T4144100 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::100 |  | 40 | 1
26820109T4144100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | MD | 194999092013 | 46 | DRESS | 165 | 165 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 495 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144100 | US WHOLESALE |  | 6.84 |  | 09T4144100 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::100 |  | 40 | 1
26820109T4144100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | LG | 194999092020 | 46 | DRESS | 107 | 107 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 321 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144100 | US WHOLESALE |  | 6.84 |  | 09T4144100 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::100 |  | 40 | 1
26820109T4144100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | XL | 194999092037 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144100 | US WHOLESALE |  | 6.84 |  | 09T4144100 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::100 |  | 40 | 1
26820109T4144100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | XXL | 194999092044 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154062 | #N/A | 09T4144100 | US WHOLESALE |  | 6.84 |  | 09T4144100 | UK0191T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4144::100 |  | 40 | 1
26820109T4159001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | MD | 194999093362 | 46 | DRESS | 304 | 304 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 912 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4159001 | US WHOLESALE |  | 6.51 |  | 09T4159001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::001 |  | 40 | 1
26820109T4159001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 194999093379 | 46 | DRESS | 190 | 190 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 570 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4159001 | US WHOLESALE |  | 6.51 |  | 09T4159001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::001 |  | 40 | 1
26820109T4159001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 194999093386 | 46 | DRESS | 69 | 69 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 207 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4159001 | US WHOLESALE |  | 6.51 |  | 09T4159001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::001 |  | 40 | 1
26820109T4159001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XXL | 194999093393 | 46 | DRESS | 78 | 78 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 234 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4159001 | US WHOLESALE |  | 6.51 |  | 09T4159001 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::001 |  | 40 | 1
26820109T4159608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | SM | 194999093607 | 46 | DRESS | 67 | 67 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 201 | BEL | Yes | 2144.9351 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4159608 | US WHOLESALE |  | 6.67 |  | 09T4159608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4159::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4159608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | MD | 194999093614 | 46 | DRESS | 381 | 381 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 1143 | BEL | Yes | 2144.9351 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4159608 | US WHOLESALE |  | 6.67 |  | 09T4159608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4159::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4159608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | LG | 194999093621 | 46 | DRESS | 268 | 268 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 804 | BEL | Yes | 2144.9351 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4159608 | US WHOLESALE |  | 6.67 |  | 09T4159608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4159::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4159608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XL | 194999093638 | 46 | DRESS | 118 | 118 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 354 | BEL | Yes | 2144.9351 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4159608 | US WHOLESALE |  | 6.67 |  | 09T4159608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4159::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4159608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XXL | 194999093645 | 46 | DRESS | 78 | 78 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 234 | BEL | Yes | 2144.9351 | 1747.9713 | 1.0932 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 154063 | #N/A | 09T4159608 | US WHOLESALE |  | 6.67 |  | 09T4159608 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 112 | -22 | 2022-01-26 | -5.1429 | -13 | 2022-01-03 | 2022-02-08 | 09T4159::608 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
26820109T4159464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | SM | 194999093553 | 46 | DRESS | 67 | 67 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 201 | BEL | Yes | 346.7355 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4159464 | US WHOLESALE |  | 6.51 |  | 09T4159464 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::464 |  | 40 | 1
26820109T4159464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | MD | 194999093560 | 46 | DRESS | 381 | 381 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 1143 | BEL | Yes | 346.7355 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4159464 | US WHOLESALE |  | 6.51 |  | 09T4159464 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::464 |  | 40 | 1
26820109T4159464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | LG | 194999093577 | 46 | DRESS | 268 | 268 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 804 | BEL | Yes | 346.7355 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4159464 | US WHOLESALE |  | 6.51 |  | 09T4159464 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::464 |  | 40 | 1
26820109T4159464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XL | 194999093584 | 46 | DRESS | 118 | 118 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 354 | BEL | Yes | 346.7355 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4159464 | US WHOLESALE |  | 6.51 |  | 09T4159464 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::464 |  | 40 | 1
26820109T4159464464 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XXL | 194999093591 | 46 | DRESS | 78 | 78 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 234 | BEL | Yes | 346.7355 | 414.5041 | 0.26168 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4159464 | US WHOLESALE |  | 6.51 |  | 09T4159464 | UK0190T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4159::464 |  | 40 | 1
26820109T4160001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | 09T4160 | Thu Cotton Stretch | 001 | 001 | BLACK | * | SM | 194999093706 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4160001 | US WHOLESALE |  | 5.34 |  | 09T4160001 | UK0189T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4160::001 |  | 40 | 1
26820109T4160001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | 09T4160 | Thu Cotton Stretch | 001 | 001 | BLACK | * | MD | 194999093713 | 46 | DRESS | 138 | 138 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 414 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4160001 | US WHOLESALE |  | 5.34 |  | 09T4160001 | UK0189T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4160::001 |  | 40 | 1
26820109T4160001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | 09T4160 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 194999093720 | 46 | DRESS | 100 | 100 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 300 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4160001 | US WHOLESALE |  | 5.34 |  | 09T4160001 | UK0189T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4160::001 |  | 40 | 1
26820109T4160001001 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | 09T4160 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 194999093737 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4160001 | US WHOLESALE |  | 5.34 |  | 09T4160001 | UK0189T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4160::001 |  | 40 | 1
26820109T4160100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | 09T4160 | Thu Cotton Stretch | 100 | 100 | WHITE | * | MD | 194999093768 | 46 | DRESS | 72 | 72 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 216 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4160100 | US WHOLESALE |  | 5.34 |  | 09T4160100 | UK0189T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4160::100 |  | 40 | 1
26820109T4160100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | 09T4160 | Thu Cotton Stretch | 100 | 100 | WHITE | * | LG | 194999093775 | 46 | DRESS | 63 | 63 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 189 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4160100 | US WHOLESALE |  | 5.34 |  | 09T4160100 | UK0189T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4160::100 |  | 40 | 1
26820109T4160100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | 09T4160 | Thu Cotton Stretch | 100 | 100 | WHITE | * | XL | 194999093782 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 180 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154065 | #N/A | 09T4160100 | US WHOLESALE |  | 5.34 |  | 09T4160100 | UK0189T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T4160::100 |  | 40 | 1
26820109TB068882882 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TB068 | 09TB068 | Thu Cotton Classics | 882 | 882 | VIBRANT ROYAL | * | 4XL | 088541742016 | 46 | DRESS | 231 | 231 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 2 | 462 | BEL | Yes | 1539.6166 | 3808.572 | 16.4873 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154056 | #N/A | 09TB068882 | US WHOLESALE |  | 6.28 |  | 09TB068882 | UK0230T |  |  | Nilushi | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TB068::882 |  | 40 | 1
26820109TE039608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | SM | 194999059122 | 46 | DRESS | 238 | 238 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 5 | 1190 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154057 | #N/A | 09TE039608 | US WHOLESALE |  | 11.58 |  | 09TE039608 | UK0246T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TE039::608 |  | 40 | 1
26820109TE039608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | MD | 194999059139 | 46 | DRESS | 676 | 676 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 5 | 3380 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154057 | #N/A | 09TE039608 | US WHOLESALE |  | 11.58 |  | 09TE039608 | UK0246T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TE039::608 |  | 40 | 1
26820109TE039608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | LG | 194999059146 | 46 | DRESS | 583 | 583 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 5 | 2915 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154057 | #N/A | 09TE039608 | US WHOLESALE |  | 11.58 |  | 09TE039608 | UK0246T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TE039::608 |  | 40 | 1
26820109TE039608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XL | 194999059153 | 46 | DRESS | 294 | 294 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 5 | 1470 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154057 | #N/A | 09TE039608 | US WHOLESALE |  | 11.58 |  | 09TE039608 | UK0246T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TE039::608 |  | 40 | 1
26820109TE039608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XXL | 194999059160 | 46 | DRESS | 168 | 168 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 5 | 840 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154057 | #N/A | 09TE039608 | US WHOLESALE |  | 11.58 |  | 09TE039608 | UK0246T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TE039::608 |  | 40 | 1
26820109TE039A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | 09TE039 | Thu Cotton Classics | A99 | 099 | MULTI | * | MD | 194999059085 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 5 | 300 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154057 | #N/A | 09TE039099 | US WHOLESALE |  | 11.96 |  | 09TE039099 | UK0246T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TE039::099 |  | 40 | 1
26820109TE039A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | 09TE039 | Thu Cotton Classics | A99 | 099 | MULTI | * | LG | 194999059092 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 5 | 300 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154057 | #N/A | 09TE039099 | US WHOLESALE |  | 11.96 |  | 09TE039099 | UK0246T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TE039::099 |  | 40 | 1
26820109TE039A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | 09TE039 | Thu Cotton Classics | A99 | 099 | MULTI | * | XL | 194999059108 | 46 | DRESS | 82 | 82 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 5 | 410 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154057 | #N/A | 09TE039099 | US WHOLESALE |  | 11.96 |  | 09TE039099 | UK0246T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TE039::099 |  | 40 | 1
26820109TE039A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | 09TE039 | Thu Cotton Classics | A99 | 099 | MULTI | * | XXL | 194999059115 | 46 | DRESS | 90 | 90 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 5 | 450 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154057 | #N/A | 09TE039099 | US WHOLESALE |  | 11.96 |  | 09TE039099 | UK0246T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TE039::099 |  | 40 | 1
26820109TF019608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | SM | 194999059672 | 46 | DRESS | 234 | 234 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 936 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019608 | US WHOLESALE |  | 7.84 |  | 09TF019608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::608 |  | 40 | 1
26820109TF019608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | MD | 194999059689 | 46 | DRESS | 832 | 832 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 3328 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019608 | US WHOLESALE |  | 7.84 |  | 09TF019608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::608 |  | 40 | 1
26820109TF019608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | LG | 194999059696 | 46 | DRESS | 686 | 686 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 2744 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019608 | US WHOLESALE |  | 7.84 |  | 09TF019608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::608 |  | 40 | 1
26820109TF019608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XL | 194999059702 | 46 | DRESS | 312 | 312 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 1248 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019608 | US WHOLESALE |  | 7.84 |  | 09TF019608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::608 |  | 40 | 1
26820109TF019608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XXL | 194999059719 | 46 | DRESS | 102 | 102 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 408 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019608 | US WHOLESALE |  | 7.84 |  | 09TF019608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::608 |  | 40 | 1
26820109TF019A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | SM | 194999059474 | 46 | DRESS | 159 | 159 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 636 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019099 | US WHOLESALE |  | 7.84 |  | 09TF019099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::099 |  | 40 | 1
26820109TF019A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | MD | 194999059481 | 46 | DRESS | 495 | 495 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 1980 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019099 | US WHOLESALE |  | 7.84 |  | 09TF019099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::099 |  | 40 | 1
26820109TF019A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | LG | 194999059498 | 46 | DRESS | 473 | 473 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 1892 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019099 | US WHOLESALE |  | 7.84 |  | 09TF019099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::099 |  | 40 | 1
26820109TF019A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | XL | 194999059504 | 46 | DRESS | 184 | 184 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 736 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019099 | US WHOLESALE |  | 7.84 |  | 09TF019099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::099 |  | 40 | 1
26820109TF019A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | XXL | 194999059511 | 46 | DRESS | 85 | 85 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 4 | 340 | BEL | Yes | 2438 | 1111.728 | 0.31211 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154058 | #N/A | 09TF019099 | US WHOLESALE |  | 7.84 |  | 09TF019099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF019::099 |  | 40 | 1
26820109TF020608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | SM | 194999059825 | 46 | DRESS | 118 | 118 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 708 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020608 | US WHOLESALE |  | 11.34 |  | 09TF020608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::608 |  | 40 | 1
26820109TF020608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | MD | 194999059832 | 46 | DRESS | 353 | 353 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 2118 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020608 | US WHOLESALE |  | 11.34 |  | 09TF020608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::608 |  | 40 | 1
26820109TF020608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | LG | 194999059849 | 46 | DRESS | 287 | 287 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 1722 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020608 | US WHOLESALE |  | 11.34 |  | 09TF020608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::608 |  | 40 | 1
26820109TF020608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XL | 194999059856 | 46 | DRESS | 134 | 134 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 804 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020608 | US WHOLESALE |  | 11.34 |  | 09TF020608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::608 |  | 40 | 1
26820109TF020608608 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XXL | 194999059863 | 46 | DRESS | 68 | 68 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 408 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020608 | US WHOLESALE |  | 11.34 |  | 09TF020608 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::608 |  | 40 | 1
26820109TF020A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | SM | 194999059771 | 46 | DRESS | 67 | 67 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 402 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020099 | US WHOLESALE |  | 11.52 |  | 09TF020099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::099 |  | 40 | 1
26820109TF020A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | MD | 194999059788 | 46 | DRESS | 176 | 176 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 1056 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020099 | US WHOLESALE |  | 11.52 |  | 09TF020099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::099 |  | 40 | 1
26820109TF020A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | LG | 194999059795 | 46 | DRESS | 135 | 135 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 810 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020099 | US WHOLESALE |  | 11.52 |  | 09TF020099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::099 |  | 40 | 1
26820109TF020A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | XL | 194999059801 | 46 | DRESS | 84 | 84 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 504 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020099 | US WHOLESALE |  | 11.52 |  | 09TF020099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::099 |  | 40 | 1
26820109TF020A99099 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | XXL | 194999059818 | 46 | DRESS | 60 | 60 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 6 | 360 | BEL | Yes | 4518 | 2304.18 | 1.5548 | Box | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 154059 | #N/A | 09TF020099 | US WHOLESALE |  | 11.52 |  | 09TF020099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 111 | 27 | 2022-01-25 | -0.14286 | 21 | 2022-01-03 | 2022-01-04 | 09TF020::099 |  | 40 | 1
26820109TV108UQF997 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | UQF | 997 | GLACIER | * | SM | 194999061170 | 46 | DRESS | 112 | 112 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 336 | BEL | Yes | 2466.8882 | 9265.632 | 12.7275 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108997 | US WHOLESALE |  | 7.05 |  | 09TV108997 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::997 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108UQF997 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | UQF | 997 | GLACIER | * | MD | 194999061187 | 46 | DRESS | 278 | 278 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 834 | BEL | Yes | 2466.8882 | 9265.632 | 12.7275 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108997 | US WHOLESALE |  | 7.05 |  | 09TV108997 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::997 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108UQF997 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | UQF | 997 | GLACIER | * | LG | 194999061194 | 46 | DRESS | 243 | 243 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 729 | BEL | Yes | 2466.8882 | 9265.632 | 12.7275 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108997 | US WHOLESALE |  | 7.05 |  | 09TV108997 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::997 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108UQF997 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | UQF | 997 | GLACIER | * | XL | 194999061200 | 46 | DRESS | 95 | 95 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 285 | BEL | Yes | 2466.8882 | 9265.632 | 12.7275 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108997 | US WHOLESALE |  | 7.05 |  | 09TV108997 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::997 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108W5Z977 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | SM | 194999061125 | 46 | DRESS | 107 | 107 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 321 | BEL | Yes | 1970.2949 | 3959.772 | 1.5011 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108977 | US WHOLESALE |  | 7.05 |  | 09TV108977 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::977 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108W5Z977 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | MD | 194999061132 | 46 | DRESS | 905 | 905 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 2715 | BEL | Yes | 1970.2949 | 3959.772 | 1.5011 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108977 | US WHOLESALE |  | 7.05 |  | 09TV108977 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::977 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108W5Z977 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | LG | 194999061149 | 46 | DRESS | 898 | 898 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 2694 | BEL | Yes | 1970.2949 | 3959.772 | 1.5011 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108977 | US WHOLESALE |  | 7.05 |  | 09TV108977 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::977 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108W5Z977 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | XL | 194999061156 | 46 | DRESS | 448 | 448 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 1344 | BEL | Yes | 1970.2949 | 3959.772 | 1.5011 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108977 | US WHOLESALE |  | 7.05 |  | 09TV108977 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::977 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108W5Z977 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | XXL | 194999061163 | 46 | DRESS | 280 | 280 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 840 | BEL | Yes | 1970.2949 | 3959.772 | 1.5011 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108977 | US WHOLESALE |  | 7.05 |  | 09TV108977 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::977 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108W6X972 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | W6X | 972 | TROUT | * | SM | 194999061071 | 46 | DRESS | 101 | 101 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 303 | BEL | Yes | 1821.8882 | 6843.012 | 4.984 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108972 | US WHOLESALE |  | 7.05 |  | 09TV108972 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::972 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108W6X972 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | W6X | 972 | TROUT | * | MD | 194999061088 | 46 | DRESS | 630 | 630 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 1890 | BEL | Yes | 1821.8882 | 6843.012 | 4.984 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108972 | US WHOLESALE |  | 7.05 |  | 09TV108972 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::972 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108W6X972 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | W6X | 972 | TROUT | * | LG | 194999061095 | 46 | DRESS | 426 | 426 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 1278 | BEL | Yes | 1821.8882 | 6843.012 | 4.984 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108972 | US WHOLESALE |  | 7.05 |  | 09TV108972 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::972 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108W6X972 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | W6X | 972 | TROUT | * | XL | 194999061101 | 46 | DRESS | 216 | 216 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 648 | BEL | Yes | 1821.8882 | 6843.012 | 4.984 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108972 | US WHOLESALE |  | 7.05 |  | 09TV108972 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-26 |  | 2021-11-19 | 85 | 86 | 1 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::972 | Supplier confirmed based on LT. Air option advised. Requested PCD 5 days advanced from STL. | 38 | 0
26820109TV108100100 | 268201 | 268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | 09TV108 | Thu Cotton Classics | 100 | 100 | WHITE | * | SM | 194999061026 | 46 | DRESS | 128 | 128 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW | 3 | 384 | BEL | Yes | 2836.6119 | 2800.8422 | 21.8816 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 154060 | #N/A | 09TV108100 | US WHOLESALE |  | 7.05 |  | 09TV108100 | UW0020T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 | 2021-11-21 |  |  | 80 | 86 | 6 | 2021-12-31 | 0 | -3 | 2022-01-03 | 2022-01-03 | 09TV108::100 |  | 43 | 0
Retail09TF001100 | Retail | A |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | SM |  | W05 | DRESS | 200 | 200 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 800 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022826 | #N/A | 09TF001100 | US RETAIL |  | 7.28 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
Retail09TF001100 | Retail | A |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | MD |  | W05 | DRESS | 600 | 600 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 2400 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022826 | #N/A | 09TF001100 | US RETAIL |  | 7.28 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
Retail09TF001100 | Retail | A |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | LG |  | W05 | DRESS | 500 | 500 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 2000 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022826 | #N/A | 09TF001100 | US RETAIL |  | 7.28 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
Retail09TF001100 | Retail | A |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | XL |  | W05 | DRESS | 200 | 200 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 800 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022826 | #N/A | 09TF001100 | US RETAIL |  | 7.28 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
Retail09TF001099 | Retail | B |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 099 | 099 | MULTI | * | SM |  | W05 | DRESS | 150 | 150 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 600 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | 4300022827 | #N/A | 09TF001099 | US RETAIL |  | 7.6 |  | 09TF001099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09TF001::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
Retail09TF001099 | Retail | B |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 099 | 099 | MULTI | * | MD |  | W05 | DRESS | 450 | 450 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 1800 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | 4300022827 | #N/A | 09TF001099 | US RETAIL |  | 7.6 |  | 09TF001099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09TF001::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
Retail09TF001099 | Retail | B |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 099 | 099 | MULTI | * | LG |  | W05 | DRESS | 300 | 300 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 1200 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | 4300022827 | #N/A | 09TF001099 | US RETAIL |  | 7.6 |  | 09TF001099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09TF001::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
Retail09TF001099 | Retail | B |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 099 | 099 | MULTI | * | XL |  | W05 | DRESS | 100 | 100 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-25 | 2022-01-18 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 400 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | Meeting the T&A delivery |  |  | 4300022827 | #N/A | 09TF001099 | US RETAIL |  | 7.6 |  | 09TF001099 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-12-18 | 2021-11-30 | 107 | 107 | 0 | 2022-01-21 | -2.1429 | 3 | 2022-01-03 | 2022-01-18 | 09TF001::099 | Supplier confirmed based on LT. Air option advised. Requested PCD 19 days advanced from STL. | 31 | 15
Retail09TF001001 | Retail | C |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | MD |  | W05 | DRESS | 400 | 400 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 1600 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022828 | #N/A | 09TF001001 | US RETAIL |  | 7.28 |  | 09TF001001 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::001 |  | 40 | 1
Retail09TF001001 | Retail | C |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | LG |  | W05 | DRESS | 250 | 250 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 1000 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022828 | #N/A | 09TF001001 | US RETAIL |  | 7.28 |  | 09TF001001 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::001 |  | 40 | 1
Retail09TF001001 | Retail | C |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | XL |  | W05 | DRESS | 150 | 150 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 600 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022828 | #N/A | 09TF001001 | US RETAIL |  | 7.28 |  | 09TF001001 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::001 |  | 40 | 1
Retail09TF001459 | Retail | D |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 459 | 459 | SOFT BLUE | * | MD |  | W05 | DRESS | 400 | 400 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 1600 | BEL | Yes | 4185.7479 | 3345.8776 | 3.3459 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022828 | #N/A | 09TF001459 | US RETAIL |  | 7.28 |  | 09TF001459 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::459 |  | 40 | 1
Retail09TF001459 | Retail | D |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | 09TF001 | THU COTTON CLASSICS | 459 | 459 | SOFT BLUE | * | LG |  | W05 | DRESS | 600 | 600 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 |  |  |  |  | S2022 |  |  | 4 | 2400 | BEL | Yes | 4185.7479 | 3345.8776 | 3.3459 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022828 | #N/A | 09TF001459 | US RETAIL |  | 7.28 |  | 09TF001459 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::459 |  | 40 | 1
Retail09R3108004 | Retail | E |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 004 | 004 | GRAYHEATHER | * | SM |  | W05 | DRESS | 150 | 150 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 | [7 empty] | 1 | 150 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 4300022832 | #N/A | 09T3108004 | US RETAIL |  | 3.18 |  | 09T3108004 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 119 | -15 | 2022-02-02 | -5.1429 | -6 | 2022-01-03 | 2022-02-08 | 09T3108::004 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
Retail09R3108004 | Retail | E |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 004 | 004 | GRAYHEATHER | * | MD |  | W05 | DRESS | 500 | 500 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 | [7 empty] | 1 | 500 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 4300022832 | #N/A | 09T3108004 | US RETAIL |  | 3.18 |  | 09T3108004 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 119 | -15 | 2022-02-02 | -5.1429 | -6 | 2022-01-03 | 2022-02-08 | 09T3108::004 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
Retail09R3108004 | Retail | E |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 004 | 004 | GRAYHEATHER | * | LG |  | W05 | DRESS | 200 | 200 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 | [7 empty] | 1 | 200 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 4300022832 | #N/A | 09T3108004 | US RETAIL |  | 3.18 |  | 09T3108004 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 119 | -15 | 2022-02-02 | -5.1429 | -6 | 2022-01-03 | 2022-02-08 | 09T3108::004 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
Retail09R3108004 | Retail | E |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 004 | 004 | GRAYHEATHER | * | XL |  | W05 | DRESS | 150 | 150 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-02-15 | 2022-02-08 | Basics-Aug 2021 | [7 empty] | 1 | 150 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  | Raw Material delay | Delay Due to RM delay |  |  | 4300022832 | #N/A | 09T3108004 | US RETAIL |  | 3.18 |  | 09T3108004 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2022-01-14 | 2022-01-07 | 134 | 119 | -15 | 2022-02-02 | -5.1429 | -6 | 2022-01-03 | 2022-02-08 | 09T3108::004 | 3 weeks RM delay due to yarn delay (Vietnam Covid situation) and PCD requested 4 weeks away from SLT with India production | 25 | 36
Retail09R3108410 | Retail | F |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 410 | 410 | DARK NAVY | * | SM |  | W05 | DRESS | 600 | 600 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 1 | 600 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022833 | #N/A | 09T3108410 | US RETAIL |  | 3.16 |  | 09T3108410 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::410 |  | 40 | 1
Retail09R3108410 | Retail | F |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 410 | 410 | DARK NAVY | * | MD |  | W05 | DRESS | 800 | 800 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 1 | 800 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022833 | #N/A | 09T3108410 | US RETAIL |  | 3.16 |  | 09T3108410 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::410 |  | 40 | 1
Retail09R3108410 | Retail | F |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 410 | 410 | DARK NAVY | * | LG |  | W05 | DRESS | 700 | 700 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 1 | 700 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022833 | #N/A | 09T3108410 | US RETAIL |  | 3.16 |  | 09T3108410 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::410 |  | 40 | 1
Retail09R3108410 | Retail | F |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 410 | 410 | DARK NAVY | * | XL |  | W05 | DRESS | 900 | 900 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 1 | 900 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022833 | #N/A | 09T3108410 | US RETAIL |  | 3.16 |  | 09T3108410 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::410 |  | 40 | 1
Retail09R3108608 | Retail | G |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 608 | 608 | MAHOGANY | * | SM |  | W05 | DRESS | 150 | 150 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 1 | 150 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022833 | #N/A | 09T3108608 | US RETAIL |  | 3.16 |  | 09T3108608 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::608 |  | 40 | 1
Retail09R3108608 | Retail | G |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 608 | 608 | MAHOGANY | * | MD |  | W05 | DRESS | 500 | 500 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 1 | 500 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022833 | #N/A | 09T3108608 | US RETAIL |  | 3.16 |  | 09T3108608 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::608 |  | 40 | 1
Retail09R3108608 | Retail | G |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 608 | 608 | MAHOGANY | * | LG |  | W05 | DRESS | 200 | 200 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 1 | 200 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022833 | #N/A | 09T3108608 | US RETAIL |  | 3.16 |  | 09T3108608 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::608 |  | 40 | 1
Retail09R3108608 | Retail | G |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3108 | 09R3108 | ATHLETIC | 608 | 608 | MAHOGANY | * | XL |  | W05 | DRESS | 150 | 150 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 1 | 150 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022833 | #N/A | 09T3108608 | US RETAIL |  | 3.16 |  | 09T3108608 | UK0002T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 84 | 0 | 2021-12-29 | -0.14286 | -6 | 2022-01-03 | 2022-01-04 | 09T3108::608 |  | 40 | 1
Retail09R3255469 | Retail | H |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09R3255 | HANGING BOXERS | 469 | 469 | ICE | * | SM |  | W05 | DRESS | 300 | 300 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 | [7 empty] | 1 | 300 | BEL | Yes | 5263.4545 | 7834.5467 | 3.4651 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 4300022834 | #N/A | 09T3255469 | US RETAIL |  | 3.38 |  | 09T3255469 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::469 |  | 42 | 0
Retail09R3255469 | Retail | H |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09R3255 | HANGING BOXERS | 469 | 469 | ICE | * | MD |  | W05 | DRESS | 1700 | 1700 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 | [7 empty] | 1 | 1700 | BEL | Yes | 5263.4545 | 7834.5467 | 3.4651 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 4300022834 | #N/A | 09T3255469 | US RETAIL |  | 3.38 |  | 09T3255469 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::469 |  | 42 | 0
Retail09R3255587 | Retail | I |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09R3255 | HANGING BOXERS | 587 | 587 | SAILOR NAVY | * | SM |  | W05 | DRESS | 500 | 500 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 | [7 empty] | 1 | 500 | BEL | Yes | 3787.4545 | 5637.5502 | 1.5086 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 4300022834 | #N/A | 09T3255587 | US RETAIL |  | 3.38 |  | 09T3255587 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::587 |  | 42 | 0
Retail09R3255587 | Retail | I |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3255 | 09R3255 | HANGING BOXERS | 587 | 587 | SAILOR NAVY | * | MD |  | W05 | DRESS | 2500 | 2500 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-10 | 2022-01-03 | Basics-Aug 2021 | [7 empty] | 1 | 2500 | BEL | Yes | 3787.4545 | 5637.5502 | 1.5086 | Fabric | 10958 - Brandix Apparel Solutions Limited - Intimate Apparel,Batticala |  |  |  | On time |  |  | 4300022834 | #N/A | 09T3255587 | US RETAIL |  | 3.38 |  | 09T3255587 | UW0021T |  |  | Thamal | Aug-Basic |  |  | 2021-09-01 | 2021-11-22 |  |  | 82 | 77 | -5 | 2021-12-22 | 0 | -12 | 2022-01-03 | 2022-01-03 | 09T3255::587 |  | 42 | 0
Retail09T3492001 | Retail | J |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3492 | 09T3492 | THU MICRO | 001 | 001 | BLACK | * | SM |  | W05 | DRESS | 100 | 100 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 3 | 300 | BEL | Yes | 200.0086 | 140.4472 | 0.1717 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022835 | #N/A | 09T3492001 | US RETAIL |  | 8.52 |  | 09T3492001 | UK0223T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3492::001 |  | 40 | 1
Retail09T3492001 | Retail | J |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3492 | 09T3492 | THU MICRO | 001 | 001 | BLACK | * | LG |  | W05 | DRESS | 300 | 300 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 3 | 900 | BEL | Yes | 200.0086 | 140.4472 | 0.1717 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022835 | #N/A | 09T3492001 | US RETAIL |  | 8.52 |  | 09T3492001 | UK0223T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3492::001 |  | 40 | 1
Retail09T3492001 | Retail | J |  |  | BRANDIX ASIA HOLDINGS PTE | 09T3492 | 09T3492 | THU MICRO | 001 | 001 | BLACK | * | XL |  | W05 | DRESS | 100 | 100 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 3 | 300 | BEL | Yes | 200.0086 | 140.4472 | 0.1717 | Fabric | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022835 | #N/A | 09T3492001 | US RETAIL |  | 8.52 |  | 09T3492001 | UK0223T |  |  | Bhagya | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 98 | 14 | 2022-01-12 | -0.14286 | 8 | 2022-01-03 | 2022-01-04 | 09T3492::001 |  | 40 | 1
RetailHCTF001100 | Retail | K |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | HCTF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | MD |  | W55 | CANADA | 200 | 200 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 4 | 800 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022837 | #N/A | 09TF001100 | CAN RETAIL |  | 7.28 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
RetailHCTF001100 | Retail | K |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | HCTF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | LG |  | W55 | CANADA | 300 | 300 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 4 | 1200 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022837 | #N/A | 09TF001100 | CAN RETAIL |  | 7.28 |  | 09TF001100 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::100 |  | 40 | 1
RetailHCTF001001 | Retail | L |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | HCTF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | MD |  | W55 | CANADA | 300 | 300 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 4 | 1200 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022837 | #N/A | 09TF001001 | CAN RETAIL |  | 7.28 |  | 09TF001001 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::001 |  | 40 | 1
RetailHCTF001001 | Retail | L |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | HCTF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | LG |  | W55 | CANADA | 100 | 100 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 4 | 400 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022837 | #N/A | 09TF001001 | CAN RETAIL |  | 7.28 |  | 09TF001001 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::001 |  | 40 | 1
RetailHCTF001001 | Retail | L |  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | HCTF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | XL |  | W55 | CANADA | 100 | 100 | 2022-03-01 |  | 2022-01-10 | 2022-01-03 | 2022-01-11 | 2022-01-04 | Basics-Aug 2021 | [7 empty] | 4 | 400 | BEL | [5 empty] | 10914 - Brandix Apparel India Pvt Ltd |  |  |  | On time |  |  | 4300022837 | #N/A | 09TF001001 | CAN RETAIL |  | 7.28 |  | 09TF001001 | UK0244T |  |  | Sheshan | Aug-Basic |  |  | 2021-09-01 |  | 2021-11-25 |  | 84 | 137 | 53 | 2022-02-20 | -0.14286 | 47 | 2022-01-03 | 2022-01-04 | 09TF001::001 |  | 40 | 1
[18 empty] | 60810 | [15 empty] | 176365
282251
105886
Formulas:
Req AC Date = [Req Sail By]-7
Cfm Sail By = [Cfm AC Date]+7
Bulk = [Bulk]+[Standered RM LT]+35
Req:del = [Req AC Date]
act: Del = [Cfm AC Date]

## Sheet6
LP00023295
LP00023297
Qty Dropped
LP00023299
LP00023298
154054
154055
154053
154052
154047
154048
154049
154050
154061
TBC
154066
154051
154062
154063
154065
154056
154057
154058
154059
154060
4300022826
4300022827
4300022828
4300022832
4300022833
4300022834
4300022835
4300022837

## Sheet3
Row Labels | Sum of Total Pcs | Model # | Merchant | 9/1 update
09T0006::099 | 12864 | UK0190T | Thamal | 9/6 IP
09T0007::099 | 21228 | UK0245T | Thamal | Dropped
09T3108::004 | 2182 | UK0244T | Sheshan | 3 IPs submitted.balance one 9/1
09T3108::410 | 4513 | UK0087T | Sheshan | Need to submit 9/1
09T3108::432 | 1146 | UK0002T | Sheshan | Need to submit 9/1
09T3108::608 | 1671 | UW0021T | Thamal | submitted
09T3255::469 | 2261 | SK0155T | Sheshan | submitted
09T3255::587 | 3737 | SK0153T | Nilushi | Need to submit 9/1
09T3255::608 | 511 | UK0191T | Sheshan | IP 9/6
09T3257::435 | 705 | UK0224T | Bhagya | IP pending .need to submit 9/1
09T3281::100 | 1105 | UK0223T | Bhagya | IP pending .need to submit 9/1
09T3283::410 | 829 | UK0194T | Bhagya | PLM error
09T3349::001 | 180 | UK0189T | Thamal | submitted
09T3351::001 | 4554 | UK0230T | Nilushi | Need to submit 9/1
09T3351::464 | 3804 | UK0246T | Thamal | submitted
09T3351::608 | 3795 | UW0020T | Bhagya | Need to submit 9/1
09T3490::001 | 219
09T3490::100 | 360
09T3490::499 | 201
09T3492::001 | 2235
09T3492::499 | 510
09T3741::608 | 1292
09T4144::001 | 1902
09T4144::100 | 1362
09T4144::464 | 2016
09T4144::608 | 2016
09T4159::001 | 1968
09T4159::464 | 2736
09T4159::608 | 2781
09T4160::001 | 1074
09T4160::100 | 585
09TB068::882 | 462
09TE039::099 | 1460
09TE039::608 | 9795
09TF001::001 | 5200
09TF001::099 | 17680
09TF001::100 | 13640
09TF001::459 | 4000
09TF019::099 | 5584
09TF019::608 | 8664
09TF020::099 | 3132
09TF020::608 | 5760
09TQ004::462 | 45
09TV108::100 | 384
09TV108::972 | 4119
09TV108::977 | 7914
09TV108::997 | 2184
Grand Total | 176365

## MA
AA | TP Style | Style | NRF Color | Model # | # of Cos | #VALUE!
268196 | 09T4159 | 09T4159 | 001 | UK0190T | 26819609T415909T4159001 | Thamal | Row Labels | Distinct Count of Model # | Distinct Count of TP Style | Distinct Count of # of Cos
268196 | 09T4159 | 09T4159 | 001 | UK0190T | 26819609T415909T4159001 | Thamal | Bhagya | 4 | 4 | 11
268196 | 09T4159 | 09T4159 | 001 | UK0190T | 26819609T415909T4159001 | Thamal | Nilushi | 2 | 2 | 2
268196 | 09T4159 | 09T4159 | 608 | UK0190T | 26819609T415909T4159608 | Thamal | Sheshan | 5 | 9 | 27
268196 | 09T4159 | 09T4159 | 608 | UK0190T | 26819609T415909T4159608 | Thamal | Thamal | 5 | 7 | 19
268196 | 09T4159 | 09T4159 | 608 | UK0190T | 26819609T415909T4159608 | Thamal | Grand Total | 16 | 22 | 59
268196 | 09TQ004 | 09TQ004 | 462 | UK0245T | 26819609TQ00409TQ004462 | Thamal
268196 | 09TQ004 | 09TQ004 | 462 | UK0245T | 26819609TQ00409TQ004462 | Thamal
268196 | 09TQ004 | 09TQ004 | 462 | UK0245T | 26819609TQ00409TQ004462 | Thamal
268197 | 09TF001 | 09TF001 | 099 | UK0244T | 26819709TF00109TF001099 | Sheshan
268197 | 09TF001 | 09TF001 | 099 | UK0244T | 26819709TF00109TF001099 | Sheshan
268197 | 09TF001 | 09TF001 | 099 | UK0244T | 26819709TF00109TF001099 | Sheshan
268197 | 09TF001 | 09TF001 | 099 | UK0244T | 26819709TF00109TF001099 | Sheshan
268197 | 09TF001 | 09TF001 | 100 | UK0244T | 26819709TF00109TF001100 | Sheshan
268197 | 09TF001 | 09TF001 | 100 | UK0244T | 26819709TF00109TF001100 | Sheshan
268197 | 09TF001 | 09TF001 | 100 | UK0244T | 26819709TF00109TF001100 | Sheshan
268197 | 09TF001 | 09TF001 | 100 | UK0244T | 26819709TF00109TF001100 | Sheshan
268201 | 09T0006 | 09T0006 | 099 | UK0087T | 26820109T000609T0006099 | Sheshan
268201 | 09T0006 | 09T0006 | 099 | UK0087T | 26820109T000609T0006099 | Sheshan
268201 | 09T0006 | 09T0006 | 099 | UK0087T | 26820109T000609T0006099 | Sheshan
268201 | 09T0006 | 09T0006 | 099 | UK0087T | 26820109T000609T0006099 | Sheshan
268201 | 09T0006 | 09T0006 | 099 | UK0087T | 26820109T000609T0006099 | Sheshan
268201 | 09T0007 | 09T0007 | 099 | UK0087T | 26820109T000709T0007099 | Sheshan
268201 | 09T0007 | 09T0007 | 099 | UK0087T | 26820109T000709T0007099 | Sheshan
268201 | 09T0007 | 09T0007 | 099 | UK0087T | 26820109T000709T0007099 | Sheshan
268201 | 09T0007 | 09T0007 | 099 | UK0087T | 26820109T000709T0007099 | Sheshan
268201 | 09T0007 | 09T0007 | 099 | UK0087T | 26820109T000709T0007099 | Sheshan
268201 | 09T3108 | 09T3108 | 410 | UK0002T | 26820109T310809T3108410 | Sheshan
268201 | 09T3108 | 09T3108 | 410 | UK0002T | 26820109T310809T3108410 | Sheshan
268201 | 09T3108 | 09T3108 | 410 | UK0002T | 26820109T310809T3108410 | Sheshan
268201 | 09T3108 | 09T3108 | 410 | UK0002T | 26820109T310809T3108410 | Sheshan
268201 | 09T3108 | 09T3108 | 432 | UK0002T | 26820109T310809T3108432 | Sheshan
268201 | 09T3108 | 09T3108 | 432 | UK0002T | 26820109T310809T3108432 | Sheshan
268201 | 09T3108 | 09T3108 | 432 | UK0002T | 26820109T310809T3108432 | Sheshan
268201 | 09T3108 | 09T3108 | 432 | UK0002T | 26820109T310809T3108432 | Sheshan
268201 | 09T3108 | 09T3108 | 004 | UK0002T | 26820109T310809T3108004 | Sheshan
268201 | 09T3108 | 09T3108 | 004 | UK0002T | 26820109T310809T3108004 | Sheshan
268201 | 09T3108 | 09T3108 | 004 | UK0002T | 26820109T310809T3108004 | Sheshan
268201 | 09T3108 | 09T3108 | 608 | UK0002T | 26820109T310809T3108608 | Sheshan
268201 | 09T3108 | 09T3108 | 608 | UK0002T | 26820109T310809T3108608 | Sheshan
268201 | 09T3108 | 09T3108 | 608 | UK0002T | 26820109T310809T3108608 | Sheshan
268201 | 09T3255 | 09T3255 | 469 | UW0021T | 26820109T325509T3255469 | Thamal
268201 | 09T3255 | 09T3255 | 608 | UW0021T | 26820109T325509T3255608 | Thamal
268201 | 09T3255 | 09T3255 | 608 | UW0021T | 26820109T325509T3255608 | Thamal
268201 | 09T3255 | 09T3255 | 608 | UW0021T | 26820109T325509T3255608 | Thamal
268201 | 09T3255 | 09T3255 | 587 | UW0021T | 26820109T325509T3255587 | Thamal
268201 | 09T3255 | 09T3255 | 587 | UW0021T | 26820109T325509T3255587 | Thamal
268201 | 09T3255 | 09T3255 | 587 | UW0021T | 26820109T325509T3255587 | Thamal
268201 | 09T3257 | 09T3257 | 435 | UW0021T | 26820109T325709T3257435 | Thamal
268201 | 09T3257 | 09T3257 | 435 | UW0021T | 26820109T325709T3257435 | Thamal
268201 | 09T3257 | 09T3257 | 435 | UW0021T | 26820109T325709T3257435 | Thamal
268201 | 09T3257 | 09T3257 | 435 | UW0021T | 26820109T325709T3257435 | Thamal
268201 | 09T3281 | 09T3281 | 100 | SK0155T | 26820109T328109T3281100 | Sheshan
268201 | 09T3281 | 09T3281 | 100 | SK0155T | 26820109T328109T3281100 | Sheshan
268201 | 09T3281 | 09T3281 | 100 | SK0155T | 26820109T328109T3281100 | Sheshan
268201 | 09T3281 | 09T3281 | 100 | SK0155T | 26820109T328109T3281100 | Sheshan
268201 | 09T3281 | 09T3281 | 100 | SK0155T | 26820109T328109T3281100 | Sheshan
268201 | 09T3283 | 09T3283 | 410 | SK0153T | 26820109T328309T3283410 | Nilushi
268201 | 09T3283 | 09T3283 | 410 | SK0153T | 26820109T328309T3283410 | Nilushi
268201 | 09T3283 | 09T3283 | 410 | SK0153T | 26820109T328309T3283410 | Nilushi
268201 | 09T3283 | 09T3283 | 410 | SK0153T | 26820109T328309T3283410 | Nilushi
268201 | 09T3349 | 09T3349 | 001 | UK0191T | 26820109T334909T3349001 | Sheshan
268201 | 09T3351 | 09T3351 | 001 | UK0190T | 26820109T335109T3351001 | Thamal
268201 | 09T3351 | 09T3351 | 001 | UK0190T | 26820109T335109T3351001 | Thamal
268201 | 09T3351 | 09T3351 | 001 | UK0190T | 26820109T335109T3351001 | Thamal
268201 | 09T3351 | 09T3351 | 608 | UK0190T | 26820109T335109T3351608 | Thamal
268201 | 09T3351 | 09T3351 | 608 | UK0190T | 26820109T335109T3351608 | Thamal
268201 | 09T3351 | 09T3351 | 608 | UK0190T | 26820109T335109T3351608 | Thamal
268201 | 09T3351 | 09T3351 | 464 | UK0190T | 26820109T335109T3351464 | Thamal
268201 | 09T3351 | 09T3351 | 464 | UK0190T | 26820109T335109T3351464 | Thamal
268201 | 09T3351 | 09T3351 | 464 | UK0190T | 26820109T335109T3351464 | Thamal
268201 | 09T3490 | 09T3490 | 001 | UK0224T | 26820109T349009T3490001 | Bhagya
268201 | 09T3490 | 09T3490 | 499 | UK0224T | 26820109T349009T3490499 | Bhagya
268201 | 09T3490 | 09T3490 | 100 | UK0224T | 26820109T349009T3490100 | Bhagya
268201 | 09T3490 | 09T3490 | 100 | UK0224T | 26820109T349009T3490100 | Bhagya
268201 | 09T3492 | 09T3492 | 001 | UK0223T | 26820109T349209T3492001 | Bhagya
268201 | 09T3492 | 09T3492 | 001 | UK0223T | 26820109T349209T3492001 | Bhagya
268201 | 09T3492 | 09T3492 | 001 | UK0223T | 26820109T349209T3492001 | Bhagya
268201 | 09T3492 | 09T3492 | 499 | UK0223T | 26820109T349209T3492499 | Bhagya
268201 | 09T3492 | 09T3492 | 499 | UK0223T | 26820109T349209T3492499 | Bhagya
268201 | 09T3741 | 09T3741 | 608 | UK0194T | 26820109T374109T3741608 | Bhagya
268201 | 09T3741 | 09T3741 | 608 | UK0194T | 26820109T374109T3741608 | Bhagya
268201 | 09T4144 | 09T4144 | 001 | UK0191T | 26820109T414409T4144001 | Sheshan
268201 | 09T4144 | 09T4144 | 001 | UK0191T | 26820109T414409T4144001 | Sheshan
268201 | 09T4144 | 09T4144 | 001 | UK0191T | 26820109T414409T4144001 | Sheshan
268201 | 09T4144 | 09T4144 | 001 | UK0191T | 26820109T414409T4144001 | Sheshan
268201 | 09T4144 | 09T4144 | 001 | UK0191T | 26820109T414409T4144001 | Sheshan
268201 | 09T4144 | 09T4144 | 608 | UK0191T | 26820109T414409T4144608 | Sheshan
268201 | 09T4144 | 09T4144 | 608 | UK0191T | 26820109T414409T4144608 | Sheshan
268201 | 09T4144 | 09T4144 | 608 | UK0191T | 26820109T414409T4144608 | Sheshan
268201 | 09T4144 | 09T4144 | 608 | UK0191T | 26820109T414409T4144608 | Sheshan
268201 | 09T4144 | 09T4144 | 608 | UK0191T | 26820109T414409T4144608 | Sheshan
268201 | 09T4144 | 09T4144 | 464 | UK0191T | 26820109T414409T4144464 | Sheshan
268201 | 09T4144 | 09T4144 | 464 | UK0191T | 26820109T414409T4144464 | Sheshan
268201 | 09T4144 | 09T4144 | 464 | UK0191T | 26820109T414409T4144464 | Sheshan
268201 | 09T4144 | 09T4144 | 464 | UK0191T | 26820109T414409T4144464 | Sheshan
268201 | 09T4144 | 09T4144 | 464 | UK0191T | 26820109T414409T4144464 | Sheshan
268201 | 09T4144 | 09T4144 | 100 | UK0191T | 26820109T414409T4144100 | Sheshan
268201 | 09T4144 | 09T4144 | 100 | UK0191T | 26820109T414409T4144100 | Sheshan
268201 | 09T4144 | 09T4144 | 100 | UK0191T | 26820109T414409T4144100 | Sheshan
268201 | 09T4144 | 09T4144 | 100 | UK0191T | 26820109T414409T4144100 | Sheshan
268201 | 09T4144 | 09T4144 | 100 | UK0191T | 26820109T414409T4144100 | Sheshan
268201 | 09T4159 | 09T4159 | 001 | UK0190T | 26820109T415909T4159001 | Thamal
268201 | 09T4159 | 09T4159 | 001 | UK0190T | 26820109T415909T4159001 | Thamal
268201 | 09T4159 | 09T4159 | 001 | UK0190T | 26820109T415909T4159001 | Thamal
268201 | 09T4159 | 09T4159 | 001 | UK0190T | 26820109T415909T4159001 | Thamal
268201 | 09T4159 | 09T4159 | 608 | UK0190T | 26820109T415909T4159608 | Thamal
268201 | 09T4159 | 09T4159 | 608 | UK0190T | 26820109T415909T4159608 | Thamal
268201 | 09T4159 | 09T4159 | 608 | UK0190T | 26820109T415909T4159608 | Thamal
268201 | 09T4159 | 09T4159 | 608 | UK0190T | 26820109T415909T4159608 | Thamal
268201 | 09T4159 | 09T4159 | 608 | UK0190T | 26820109T415909T4159608 | Thamal
268201 | 09T4159 | 09T4159 | 464 | UK0190T | 26820109T415909T4159464 | Thamal
268201 | 09T4159 | 09T4159 | 464 | UK0190T | 26820109T415909T4159464 | Thamal
268201 | 09T4159 | 09T4159 | 464 | UK0190T | 26820109T415909T4159464 | Thamal
268201 | 09T4159 | 09T4159 | 464 | UK0190T | 26820109T415909T4159464 | Thamal
268201 | 09T4159 | 09T4159 | 464 | UK0190T | 26820109T415909T4159464 | Thamal
268201 | 09T4160 | 09T4160 | 001 | UK0189T | 26820109T416009T4160001 | Thamal
268201 | 09T4160 | 09T4160 | 001 | UK0189T | 26820109T416009T4160001 | Thamal
268201 | 09T4160 | 09T4160 | 001 | UK0189T | 26820109T416009T4160001 | Thamal
268201 | 09T4160 | 09T4160 | 001 | UK0189T | 26820109T416009T4160001 | Thamal
268201 | 09T4160 | 09T4160 | 100 | UK0189T | 26820109T416009T4160100 | Thamal
268201 | 09T4160 | 09T4160 | 100 | UK0189T | 26820109T416009T4160100 | Thamal
268201 | 09T4160 | 09T4160 | 100 | UK0189T | 26820109T416009T4160100 | Thamal
268201 | 09TB068 | 09TB068 | 882 | UK0230T | 26820109TB06809TB068882 | Nilushi
268201 | 09TE039 | 09TE039 | 608 | UK0246T | 26820109TE03909TE039608 | Thamal
268201 | 09TE039 | 09TE039 | 608 | UK0246T | 26820109TE03909TE039608 | Thamal
268201 | 09TE039 | 09TE039 | 608 | UK0246T | 26820109TE03909TE039608 | Thamal
268201 | 09TE039 | 09TE039 | 608 | UK0246T | 26820109TE03909TE039608 | Thamal
268201 | 09TE039 | 09TE039 | 608 | UK0246T | 26820109TE03909TE039608 | Thamal
268201 | 09TE039 | 09TE039 | 099 | UK0246T | 26820109TE03909TE039099 | Thamal
268201 | 09TE039 | 09TE039 | 099 | UK0246T | 26820109TE03909TE039099 | Thamal
268201 | 09TE039 | 09TE039 | 099 | UK0246T | 26820109TE03909TE039099 | Thamal
268201 | 09TE039 | 09TE039 | 099 | UK0246T | 26820109TE03909TE039099 | Thamal
268201 | 09TF019 | 09TF019 | 608 | UK0244T | 26820109TF01909TF019608 | Sheshan
268201 | 09TF019 | 09TF019 | 608 | UK0244T | 26820109TF01909TF019608 | Sheshan
268201 | 09TF019 | 09TF019 | 608 | UK0244T | 26820109TF01909TF019608 | Sheshan
268201 | 09TF019 | 09TF019 | 608 | UK0244T | 26820109TF01909TF019608 | Sheshan
268201 | 09TF019 | 09TF019 | 608 | UK0244T | 26820109TF01909TF019608 | Sheshan
268201 | 09TF019 | 09TF019 | 099 | UK0244T | 26820109TF01909TF019099 | Sheshan
268201 | 09TF019 | 09TF019 | 099 | UK0244T | 26820109TF01909TF019099 | Sheshan
268201 | 09TF019 | 09TF019 | 099 | UK0244T | 26820109TF01909TF019099 | Sheshan
268201 | 09TF019 | 09TF019 | 099 | UK0244T | 26820109TF01909TF019099 | Sheshan
268201 | 09TF019 | 09TF019 | 099 | UK0244T | 26820109TF01909TF019099 | Sheshan
268201 | 09TF020 | 09TF020 | 608 | UK0244T | 26820109TF02009TF020608 | Sheshan
268201 | 09TF020 | 09TF020 | 608 | UK0244T | 26820109TF02009TF020608 | Sheshan
268201 | 09TF020 | 09TF020 | 608 | UK0244T | 26820109TF02009TF020608 | Sheshan
268201 | 09TF020 | 09TF020 | 608 | UK0244T | 26820109TF02009TF020608 | Sheshan
268201 | 09TF020 | 09TF020 | 608 | UK0244T | 26820109TF02009TF020608 | Sheshan
268201 | 09TF020 | 09TF020 | 099 | UK0244T | 26820109TF02009TF020099 | Sheshan
268201 | 09TF020 | 09TF020 | 099 | UK0244T | 26820109TF02009TF020099 | Sheshan
268201 | 09TF020 | 09TF020 | 099 | UK0244T | 26820109TF02009TF020099 | Sheshan
268201 | 09TF020 | 09TF020 | 099 | UK0244T | 26820109TF02009TF020099 | Sheshan
268201 | 09TF020 | 09TF020 | 099 | UK0244T | 26820109TF02009TF020099 | Sheshan
268201 | 09TV108 | 09TV108 | 997 | UW0020T | 26820109TV10809TV108997 | Bhagya
268201 | 09TV108 | 09TV108 | 997 | UW0020T | 26820109TV10809TV108997 | Bhagya
268201 | 09TV108 | 09TV108 | 997 | UW0020T | 26820109TV10809TV108997 | Bhagya
268201 | 09TV108 | 09TV108 | 997 | UW0020T | 26820109TV10809TV108997 | Bhagya
268201 | 09TV108 | 09TV108 | 977 | UW0020T | 26820109TV10809TV108977 | Bhagya
268201 | 09TV108 | 09TV108 | 977 | UW0020T | 26820109TV10809TV108977 | Bhagya
268201 | 09TV108 | 09TV108 | 977 | UW0020T | 26820109TV10809TV108977 | Bhagya
268201 | 09TV108 | 09TV108 | 977 | UW0020T | 26820109TV10809TV108977 | Bhagya
268201 | 09TV108 | 09TV108 | 977 | UW0020T | 26820109TV10809TV108977 | Bhagya
268201 | 09TV108 | 09TV108 | 972 | UW0020T | 26820109TV10809TV108972 | Bhagya
268201 | 09TV108 | 09TV108 | 972 | UW0020T | 26820109TV10809TV108972 | Bhagya
268201 | 09TV108 | 09TV108 | 972 | UW0020T | 26820109TV10809TV108972 | Bhagya
268201 | 09TV108 | 09TV108 | 972 | UW0020T | 26820109TV10809TV108972 | Bhagya
268201 | 09TV108 | 09TV108 | 100 | UW0020T | 26820109TV10809TV108100 | Bhagya
A | 09TF001 | 09TF001 | 100 | UK0244T | A09TF00109TF001100 | Sheshan
A | 09TF001 | 09TF001 | 100 | UK0244T | A09TF00109TF001100 | Sheshan
A | 09TF001 | 09TF001 | 100 | UK0244T | A09TF00109TF001100 | Sheshan
A | 09TF001 | 09TF001 | 100 | UK0244T | A09TF00109TF001100 | Sheshan
B | 09TF001 | 09TF001 | 099 | UK0244T | B09TF00109TF001099 | Sheshan
B | 09TF001 | 09TF001 | 099 | UK0244T | B09TF00109TF001099 | Sheshan
B | 09TF001 | 09TF001 | 099 | UK0244T | B09TF00109TF001099 | Sheshan
B | 09TF001 | 09TF001 | 099 | UK0244T | B09TF00109TF001099 | Sheshan
C | 09TF001 | 09TF001 | 001 | UK0244T | C09TF00109TF001001 | Sheshan
C | 09TF001 | 09TF001 | 001 | UK0244T | C09TF00109TF001001 | Sheshan
C | 09TF001 | 09TF001 | 001 | UK0244T | C09TF00109TF001001 | Sheshan
D | 09TF001 | 09TF001 | 459 | UK0244T | D09TF00109TF001459 | Sheshan
D | 09TF001 | 09TF001 | 459 | UK0244T | D09TF00109TF001459 | Sheshan
E | 09T3108 | 09R3108 | 004 | UK0002T | E09T310809R3108004 | Sheshan
E | 09T3108 | 09R3108 | 004 | UK0002T | E09T310809R3108004 | Sheshan
E | 09T3108 | 09R3108 | 004 | UK0002T | E09T310809R3108004 | Sheshan
E | 09T3108 | 09R3108 | 004 | UK0002T | E09T310809R3108004 | Sheshan
F | 09T3108 | 09R3108 | 410 | UK0002T | F09T310809R3108410 | Sheshan
F | 09T3108 | 09R3108 | 410 | UK0002T | F09T310809R3108410 | Sheshan
F | 09T3108 | 09R3108 | 410 | UK0002T | F09T310809R3108410 | Sheshan
F | 09T3108 | 09R3108 | 410 | UK0002T | F09T310809R3108410 | Sheshan
G | 09T3108 | 09R3108 | 608 | UK0002T | G09T310809R3108608 | Sheshan
G | 09T3108 | 09R3108 | 608 | UK0002T | G09T310809R3108608 | Sheshan
G | 09T3108 | 09R3108 | 608 | UK0002T | G09T310809R3108608 | Sheshan
G | 09T3108 | 09R3108 | 608 | UK0002T | G09T310809R3108608 | Sheshan
H | 09T3255 | 09R3255 | 469 | UW0021T | H09T325509R3255469 | Thamal
H | 09T3255 | 09R3255 | 469 | UW0021T | H09T325509R3255469 | Thamal
I | 09T3255 | 09R3255 | 587 | UW0021T | I09T325509R3255587 | Thamal
I | 09T3255 | 09R3255 | 587 | UW0021T | I09T325509R3255587 | Thamal
J | 09T3492 | 09T3492 | 001 | UK0223T | J09T349209T3492001 | Bhagya
J | 09T3492 | 09T3492 | 001 | UK0223T | J09T349209T3492001 | Bhagya
J | 09T3492 | 09T3492 | 001 | UK0223T | J09T349209T3492001 | Bhagya
K | 09TF001 | HCTF001 | 100 | UK0244T | K09TF001HCTF001100 | Sheshan
K | 09TF001 | HCTF001 | 100 | UK0244T | K09TF001HCTF001100 | Sheshan
L | 09TF001 | HCTF001 | 001 | UK0244T | L09TF001HCTF001001 | Sheshan
L | 09TF001 | HCTF001 | 001 | UK0244T | L09TF001HCTF001001 | Sheshan
L | 09TF001 | HCTF001 | 001 | UK0244T | L09TF001HCTF001001 | Sheshan

## WHOLESALE (hidden)
AA | Buy Plan | Vendor | Vendor Name | Style | Program Name | Color | NRF Color | Color Name | Dimension | Size | UPC | Ship to | Office | Qty | Need By | In DC Date | Req Sail By | Req AC Date | Cfm Sail By | Cfm AC Date | Buy Period | Prepack Style | Prepack Color | Prepack Description | Licensee | Cost Folio Season | Comment | Process Step
268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | MD | 194999093362 |  | DRESS | 5 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 194999093379 |  | DRESS | 5 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 194999093386 |  | DRESS | 5 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | MD | 194999093614 |  | DRESS | 5 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | LG | 194999093621 |  | DRESS | 5 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XL | 194999093638 |  | DRESS | 5 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TQ004 | Thu Cotton Classics | U76 | 462 | INK BLUE | * | MD | 088541601627 |  | DRESS | 5 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TQ004 | Thu Cotton Classics | U76 | 462 | INK BLUE | * | LG | 088541601634 |  | DRESS | 5 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268196 | 36660 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TQ004 | Thu Cotton Classics | U76 | 462 | INK BLUE | * | XL | 088541601641 |  | DRESS | 5 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | Thu Cotton Classics | A99 | 099 | MULTI | * | SM | 088541316606 |  | DRESS | 800 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW
268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | Thu Cotton Classics | A99 | 099 | MULTI | * | MD | 088541316613 |  | DRESS | 890 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW
268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | Thu Cotton Classics | A99 | 099 | MULTI | * | LG | 088541316620 |  | DRESS | 1140 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW
268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | Thu Cotton Classics | A99 | 099 | MULTI | * | XL | 088541316637 |  | DRESS | 590 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW
268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | Thu Cotton Classics | 100 | 100 | WHITE | * | SM | 088541316651 |  | DRESS | 400 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW
268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | Thu Cotton Classics | 100 | 100 | WHITE | * | MD | 088541316668 |  | DRESS | 420 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW
268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | Thu Cotton Classics | 100 | 100 | WHITE | * | LG | 088541316675 |  | DRESS | 470 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW
268197 | 36662 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF001 | Thu Cotton Classics | 100 | 100 | WHITE | * | XL | 088541316682 |  | DRESS | 120 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  | JV-Baseco S.A.P.I. de C.V. | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | S | 088541003544 | 46 | DRESS | 312 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | M | 088541003551 | 46 | DRESS | 1210 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | L | 088541003568 | 46 | DRESS | 969 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | XL | 088541003575 | 46 | DRESS | 593 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0006 | Thu Cotton Classics | 099 | 099 | MULTI | * | 2XL | 088541003582 | 46 | DRESS | 132 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | S | 088541003599 | 46 | DRESS | 586 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | M | 088541003605 | 46 | DRESS | 2035 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | L | 088541003612 | 46 | DRESS | 1265 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | XL | 088541003629 | 46 | DRESS | 850 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T0007 | Thu Cotton Classics | 099 | 099 | MULTI | * | 2XL | 088541003636 | 46 | DRESS | 571 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | CHS | 410 | DARK NAVY | * | SM | 088541378727 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | CHS | 410 | DARK NAVY | * | MD | 088541378734 | 46 | DRESS | 231 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | CHS | 410 | DARK NAVY | * | LG | 088541378741 | 46 | DRESS | 539 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | CHS | 410 | DARK NAVY | * | XL | 088541378758 | 46 | DRESS | 683 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | CIX | 432 | French Blue | * | SM | 088541378772 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | CIX | 432 | French Blue | * | MD | 088541378789 | 46 | DRESS | 362 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | CIX | 432 | French Blue | * | LG | 088541378796 | 46 | DRESS | 395 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | CIX | 432 | French Blue | * | XL | 088541378802 | 46 | DRESS | 329 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | P7A | 004 | Grey Heather | * | MD | 088541378680 | 46 | DRESS | 417 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | P7A | 004 | Grey Heather | * | LG | 088541378697 | 46 | DRESS | 660 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | P7A | 004 | Grey Heather | * | XL | 088541378703 | 46 | DRESS | 105 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | XCN | 608 | Mahogany | * | MD | 088541378833 | 46 | DRESS | 221 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | XCN | 608 | Mahogany | * | LG | 088541378840 | 46 | DRESS | 109 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3108 | Thu Cotton Classics | XCN | 608 | Mahogany | * | XL | 088541378857 | 46 | DRESS | 341 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | Hanging Boxers | 469 | 469 | ICE | * | XXL | 088541450966 | 46 | DRESS | 261 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | Hanging Boxers | 608 | 608 | MAHOGANY | * | MD | 088541451031 | 46 | DRESS | 227 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | Hanging Boxers | 608 | 608 | MAHOGANY | * | LG | 088541451048 | 46 | DRESS | 224 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | Hanging Boxers | 608 | 608 | MAHOGANY | * | XXL | 088541451062 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | Hanging Boxers | 410 | 587 | SAILOR NAVY | * | MD | 088541450980 | 46 | DRESS | 312 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | Hanging Boxers | 410 | 587 | SAILOR NAVY | * | LG | 088541450997 | 46 | DRESS | 308 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3255 | Hanging Boxers | 410 | 587 | SAILOR NAVY | * | XL | 088541451000 | 46 | DRESS | 117 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3257 | Hanging Boxers | F1S | 435 | INDIGO | * | SM | 088541451079 | 46 | DRESS | 84 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3257 | Hanging Boxers | F1S | 435 | INDIGO | * | MD | 088541451086 | 46 | DRESS | 136 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3257 | Hanging Boxers | F1S | 435 | INDIGO | * | LG | 088541451093 | 46 | DRESS | 150 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3257 | Hanging Boxers | F1S | 435 | INDIGO | * | XL | 088541451109 | 46 | DRESS | 335 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | Modern Essentials | YC7 | 100 | White | * | SM | 088541492652 | 46 | DRESS | 116 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | Modern Essentials | YC7 | 100 | White | * | MD | 088541492669 | 46 | DRESS | 328 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | Modern Essentials | YC7 | 100 | White | * | LG | 088541492676 | 46 | DRESS | 439 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | Modern Essentials | YC7 | 100 | White | * | XL | 088541492683 | 46 | DRESS | 115 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3281 | Modern Essentials | YC7 | 100 | White | * | XXL | 088541492690 | 46 | DRESS | 107 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3283 | Modern Essentials | CHS | 410 | DARK NAVY | * | SM | 088541492751 | 46 | DRESS | 221 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3283 | Modern Essentials | CHS | 410 | DARK NAVY | * | MD | 088541492768 | 46 | DRESS | 212 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3283 | Modern Essentials | CHS | 410 | DARK NAVY | * | LG | 088541492775 | 46 | DRESS | 301 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3283 | Modern Essentials | CHS | 410 | DARK NAVY | * | XXL | 088541492799 | 46 | DRESS | 95 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3349 | Thu Cotton Stretch | UB1 | 001 | Black | * | XL | 088541539296 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 088541539739 | 46 | DRESS | 676 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 088541539746 | 46 | DRESS | 747 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XXL | 088541539753 | 46 | DRESS | 95 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | LG | 088541539487 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XL | 088541539494 | 46 | DRESS | 1133 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XXL | 088541539500 | 46 | DRESS | 72 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | SM | 088541542739 | 46 | DRESS | 218 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | LG | 088541542753 | 46 | DRESS | 461 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3351 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XL | 088541542760 | 46 | DRESS | 589 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3490 | Thu Micro | 001 | 001 | BLACK | * | XXL | 088541654623 | 46 | DRESS | 73 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3490 | Thu Micro | 499 | 499 | BLUE MULTI | * | LG | 088541654753 | 46 | DRESS | 67 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3490 | Thu Micro | 100 | 100 | WHITE | * | MD | 088541654647 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3490 | Thu Micro | 100 | 100 | WHITE | * | XL | 088541654661 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | Thu Micro | 001 | 001 | BLACK | * | MD | 088541654890 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | Thu Micro | 001 | 001 | BLACK | * | LG | 088541654906 | 46 | DRESS | 125 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | Thu Micro | 001 | 001 | BLACK | * | XXL | 088541654920 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | Thu Micro | 499 | 499 | BLUE MULTI | * | MD | 088541654999 | 46 | DRESS | 93 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3492 | Thu Micro | 499 | 499 | BLUE MULTI | * | LG | 088541655002 | 46 | DRESS | 77 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3741 | Modern Essentials | 608 | 608 | MAHOGANY | * | MD | 088541946582 | 46 | DRESS | 239 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T3741 | Modern Essentials | 608 | 608 | MAHOGANY | * | LG | 088541946599 | 46 | DRESS | 84 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | SM | 194999091955 | 46 | DRESS | 70 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | MD | 194999091962 | 46 | DRESS | 255 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 194999091979 | 46 | DRESS | 187 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 194999091986 | 46 | DRESS | 62 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XXL | 194999091993 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | SM | 194999092259 | 46 | DRESS | 70 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | MD | 194999092266 | 46 | DRESS | 255 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | LG | 194999092273 | 46 | DRESS | 207 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XL | 194999092280 | 46 | DRESS | 80 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XXL | 194999092297 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | SM | 194999092204 | 46 | DRESS | 70 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | MD | 194999092211 | 46 | DRESS | 255 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | LG | 194999092228 | 46 | DRESS | 207 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XL | 194999092235 | 46 | DRESS | 80 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XXL | 194999092242 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | SM | 194999092006 | 46 | DRESS | 62 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | MD | 194999092013 | 46 | DRESS | 165 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | LG | 194999092020 | 46 | DRESS | 107 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | XL | 194999092037 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4144 | Thu Cotton Stretch | 100 | 100 | WHITE | * | XXL | 194999092044 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | MD | 194999093362 | 46 | DRESS | 304 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 194999093379 | 46 | DRESS | 190 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 194999093386 | 46 | DRESS | 69 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XXL | 194999093393 | 46 | DRESS | 78 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | SM | 194999093607 | 46 | DRESS | 67 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | MD | 194999093614 | 46 | DRESS | 381 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | LG | 194999093621 | 46 | DRESS | 268 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XL | 194999093638 | 46 | DRESS | 118 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 608 | 608 | MAHOGANY | * | XXL | 194999093645 | 46 | DRESS | 78 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | SM | 194999093553 | 46 | DRESS | 67 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | MD | 194999093560 | 46 | DRESS | 381 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | LG | 194999093577 | 46 | DRESS | 268 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XL | 194999093584 | 46 | DRESS | 118 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4159 | Thu Cotton Stretch | 464 | 464 | PERSIAN BLUE | * | XXL | 194999093591 | 46 | DRESS | 78 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | Thu Cotton Stretch | 001 | 001 | BLACK | * | SM | 194999093706 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | Thu Cotton Stretch | 001 | 001 | BLACK | * | MD | 194999093713 | 46 | DRESS | 138 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | Thu Cotton Stretch | 001 | 001 | BLACK | * | LG | 194999093720 | 46 | DRESS | 100 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | Thu Cotton Stretch | 001 | 001 | BLACK | * | XL | 194999093737 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | Thu Cotton Stretch | 100 | 100 | WHITE | * | MD | 194999093768 | 46 | DRESS | 72 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | Thu Cotton Stretch | 100 | 100 | WHITE | * | LG | 194999093775 | 46 | DRESS | 63 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09T4160 | Thu Cotton Stretch | 100 | 100 | WHITE | * | XL | 194999093782 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TB068 | Thu Cotton Classics | 882 | 882 | VIBRANT ROYAL | * | 4XL | 088541742016 | 46 | DRESS | 231 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | SM | 194999059122 | 46 | DRESS | 238 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | MD | 194999059139 | 46 | DRESS | 676 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | LG | 194999059146 | 46 | DRESS | 583 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XL | 194999059153 | 46 | DRESS | 294 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XXL | 194999059160 | 46 | DRESS | 168 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | Thu Cotton Classics | A99 | 099 | MULTI | * | MD | 194999059085 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | Thu Cotton Classics | A99 | 099 | MULTI | * | LG | 194999059092 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | Thu Cotton Classics | A99 | 099 | MULTI | * | XL | 194999059108 | 46 | DRESS | 82 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TE039 | Thu Cotton Classics | A99 | 099 | MULTI | * | XXL | 194999059115 | 46 | DRESS | 90 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | SM | 194999059672 | 46 | DRESS | 234 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | MD | 194999059689 | 46 | DRESS | 832 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | LG | 194999059696 | 46 | DRESS | 686 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XL | 194999059702 | 46 | DRESS | 312 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XXL | 194999059719 | 46 | DRESS | 102 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | SM | 194999059474 | 46 | DRESS | 159 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | MD | 194999059481 | 46 | DRESS | 495 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | LG | 194999059498 | 46 | DRESS | 473 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | XL | 194999059504 | 46 | DRESS | 184 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF019 | Thu Cotton Classics | A99 | 099 | MULTI | * | XXL | 194999059511 | 46 | DRESS | 85 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | SM | 194999059825 | 46 | DRESS | 118 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | MD | 194999059832 | 46 | DRESS | 353 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | LG | 194999059849 | 46 | DRESS | 287 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XL | 194999059856 | 46 | DRESS | 134 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | 608 | 608 | MAHOGANY | * | XXL | 194999059863 | 46 | DRESS | 68 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | SM | 194999059771 | 46 | DRESS | 67 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | MD | 194999059788 | 46 | DRESS | 176 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | LG | 194999059795 | 46 | DRESS | 135 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | XL | 194999059801 | 46 | DRESS | 84 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TF020 | Thu Cotton Classics | A99 | 099 | MULTI | * | XXL | 194999059818 | 46 | DRESS | 60 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | UQF | 997 | GLACIER | * | SM | 194999061170 | 46 | DRESS | 112 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | UQF | 997 | GLACIER | * | MD | 194999061187 | 46 | DRESS | 278 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | UQF | 997 | GLACIER | * | LG | 194999061194 | 46 | DRESS | 243 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | UQF | 997 | GLACIER | * | XL | 194999061200 | 46 | DRESS | 95 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | SM | 194999061125 | 46 | DRESS | 107 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | MD | 194999061132 | 46 | DRESS | 905 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | LG | 194999061149 | 46 | DRESS | 898 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | XL | 194999061156 | 46 | DRESS | 448 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | W5Z | 977 | PARIS BLUE | * | XXL | 194999061163 | 46 | DRESS | 280 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | W6X | 972 | TROUT | * | SM | 194999061071 | 46 | DRESS | 101 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | W6X | 972 | TROUT | * | MD | 194999061088 | 46 | DRESS | 630 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | W6X | 972 | TROUT | * | LG | 194999061095 | 46 | DRESS | 426 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | W6X | 972 | TROUT | * | XL | 194999061101 | 46 | DRESS | 216 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW
268201 | 36663 | 11317 | BRANDIX ASIA HOLDINGS PTE | 09TV108 | Thu Cotton Classics | 100 | 100 | WHITE | * | SM | 194999061026 | 46 | DRESS | 128 | 2022-03-01 |  | 1/10/2022 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022 |  | OPS REVIEW

## RETAIL (hidden)
AA | Buy Plan | Vendor | Vendor Name | Style | Program Name | Color | NRF Color | Color Name | Dimension | Size | UPC | Ship to | Office | Qty | Need By | In DC Date | Req Sail By | Req AC Date | Cfm Sail By | Cfm AC Date | Buy Period | Prepack Style | Prepack Color | Prepack Description | Licensee | Cost Folio Season | Comment | Process Step
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | SM |  | W05 | DRESS | 200 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | MD |  | W05 | DRESS | 600 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | LG |  | W05 | DRESS | 500 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | XL |  | W05 | DRESS | 200 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 099 | 099 | MULTI | * | SM |  | W05 | DRESS | 150 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 099 | 099 | MULTI | * | MD |  | W05 | DRESS | 450 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 099 | 099 | MULTI | * | LG |  | W05 | DRESS | 300 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 099 | 099 | MULTI | * | XL |  | W05 | DRESS | 100 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | MD |  | W05 | DRESS | 400 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | LG |  | W05 | DRESS | 250 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | XL |  | W05 | DRESS | 150 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 459 | 459 | SOFT BLUE | * | MD |  | W05 | DRESS | 400 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09TF001 | THU COTTON CLASSICS | 459 | 459 | SOFT BLUE | * | LG |  | W05 | DRESS | 600 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021 |  |  |  |  | S2022
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 004 | 004 | GRAYHEATHER | * | SM |  | W05 | DRESS | 150 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 004 | 004 | GRAYHEATHER | * | MD |  | W05 | DRESS | 500 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 004 | 004 | GRAYHEATHER | * | LG |  | W05 | DRESS | 200 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 004 | 004 | GRAYHEATHER | * | XL |  | W05 | DRESS | 150 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 410 | 410 | DARK NAVY | * | SM |  | W05 | DRESS | 600 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 410 | 410 | DARK NAVY | * | MD |  | W05 | DRESS | 800 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 410 | 410 | DARK NAVY | * | LG |  | W05 | DRESS | 700 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 410 | 410 | DARK NAVY | * | XL |  | W05 | DRESS | 900 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 608 | 608 | MAHOGANY | * | SM |  | W05 | DRESS | 150 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 608 | 608 | MAHOGANY | * | MD |  | W05 | DRESS | 500 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 608 | 608 | MAHOGANY | * | LG |  | W05 | DRESS | 200 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3108 | ATHLETIC | 608 | 608 | MAHOGANY | * | XL |  | W05 | DRESS | 150 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3255 | HANGING BOXERS | 469 | 469 | ICE | * | SM |  | W05 | DRESS | 300 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3255 | HANGING BOXERS | 469 | 469 | ICE | * | MD |  | W05 | DRESS | 1700 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3255 | HANGING BOXERS | 587 | 587 | SAILOR NAVY | * | SM |  | W05 | DRESS | 500 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09R3255 | HANGING BOXERS | 587 | 587 | SAILOR NAVY | * | MD |  | W05 | DRESS | 2500 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09T3492 | THU MICRO | 001 | 001 | BLACK | * | SM |  | W05 | DRESS | 100 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09T3492 | THU MICRO | 001 | 001 | BLACK | * | LG |  | W05 | DRESS | 300 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | 09T3492 | THU MICRO | 001 | 001 | BLACK | * | XL |  | W05 | DRESS | 100 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | HCTF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | MD |  | W55 | CANADA | 200 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | HCTF001 | THU COTTON CLASSICS | 100 | 100 | WHITE | * | LG |  | W55 | CANADA | 300 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | HCTF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | MD |  | W55 | CANADA | 300 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | HCTF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | LG |  | W55 | CANADA | 100 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021
|  |  | BRANDIX ASIA HOLDINGS PTE | HCTF001 | THU COTTON CLASSICS | 001 | 001 | BLACK | * | XL |  | W55 | CANADA | 100 | 2022-03-01 |  | 2022-01-10 |  |  |  | Basics-Aug 2021

## Sheet4 (hidden)
Sum of Total Pcs | Years | Req AC Date
| 2022 | Grand Total
Plant | Jan
BEL | 143665 | 143665
Grand Total | 143665 | 143665

## List (hidden)
Capacity Constraints
EC Required
Production Efficiency
Late AA / Order
Raw Material delay
Non-recurring
MOQ/MCQ Issues

## Sheet2 (hidden)
OPS OPEN BUY PLAN REPORT - 8/16/2021 12:07:35 PM
Filter(s) selected in this report
Company: | Canada,Dress
Division: | PVH UNDERWEAR-09,TH CANADA UNDERWEAR-HC
Buy Period Season: | Basics-Aug
Buy Period Year: | 2021